**Annexure C**

**Confidential Reporting form C**

**EXECUTIVE SUMMARY OF THE EVALUATION**

**(Submitted to SACS for each TI evaluated with a copy to DAC)**

**Profile of the evaluator(s):**

|  |  |
| --- | --- |
| **Name of the evaluators** | **Contact Details with phone no.** |
| **Mathivanan Ramachandran** | [**ira.mathivanan@gmail.com**](mailto:ira.mathivanan@gmail.com)**, 09840231989** |
| **Shaik Imthiaz Ahmmed** | [**reehana.ahmed@gmail.com**](mailto:reehana.ahmed@gmail.com)**, 09248350197** |
| **Officials from SACS/TSU (as facilitator)** |  |

|  |  |
| --- | --- |
| **Name of the NGO:** | **RashtrasantTukdojiMaharajSikshan&ArgyaPrasarak Mandal** |
| **Typology of the target population:** | **Core – FSW** |
| **Total population being covered against target:** | **779 active against 800 contracted** |
| **Dates of Visit:** | **20, 21 & 24 April 2016** |
| **Place of Visit:** | **Amravati Rural** |

Overall Rating based programme delivery score:

|  |  |  |  |
| --- | --- | --- | --- |
| **Total Score Obtained (in %)** | **Category** | **Rating** | **Recommendations** |
| **Below 40%** | **D** | **Poor** | **Recommended for** |
| **41%-60%** | **C** | **Average** | **Recommended for** |
| **61%-80%** | **B** | **Good** | **Recommended for** |
| ***>80%*** | ***A*** | ***Very Good*** | ***Recommended for continuation ~~with specific focus for developing learning sites.~~*** |

**Specific Recommendations:**

|  |
| --- |
| **Though this organisation has scored more tahn80% at programme delivery and more in finance and just qualified in capacity building it could not be recommended for developing learning sites at present because of the following concerns to be addressed.**   * **The achievement percentage in RMC, ICTC, clinic visit and counselled are shown high.** * **PM needs to be further trained and motivated and could be replaced if required.** * **Computerised documentation has been done by external person as M&E and PM struggled with.** * **Review meetings need to discuss the gaps and prioritising the components to be achieved, suggestions to staffs and action taken points** * **Though they have community support and government support at large level, Community participation needs to be strengthened in programme planning and implementation and documented.** * **Specific recommendation to NACO: *THIS MAY BE THE RIGHT TIME TO MODIFY THE TOOL*** |

**Name of the Evaluators Signature**

|  |  |
| --- | --- |
| **Mathivanan Ramachandran** |  |
| **Shaik Imthiaz Ahmmed** |  |
| **Pravin Mhasal-Finance** |  |