Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

- Background of Project and Organisation:

Janhitay Mandal instablish in  1992 and started working on health education , women and child related aspects mainly reproductive health, immunization, health check up camps in the vicinity of Chandrapur. JANHITAY MANDAL (J.H.M.) Chandrapur registered under Society Registration Act 1860 vide Dated 07/02/1992 and Mumbai Public Trust Act - 1950 No. 19 Regd.Dated 29/06/1992,The organization is implementing targeted intervention (TI) project on (destination) migrants in the district of Chandrapur in the state of Maharashtra as one the partners of Maharshtra State AIDS Control Society (MSACS) since December 2008. Majority of project beneficiaries of this migrant TI belonged to the states of Bihar and Uttar Pradesh,Chatisgarh,Andra Pradesh,Uttar Pradesh,Odisha,Rajisthan ,Panjab,West Bangal,Jharkhand,Mahrashtra HRG migrants (HRGM).

| Name of the Project | Funded By | Year | Working Area |
| --- | --- | --- | --- |
| Jhep De-addiction Treatment Cum Rehabilitation Centre | Ministry of Social Justice & Empowerment | Year 2000 | De- Addiction |
| Targeted Intervention for Migrant Project | MSACS, Mumbai | Year Dec 2008 | Intervention with Migrant people HIV/AIDS, STI |
| Prevention of Parents to child transmission Project | IL & FSETS, Noida | Year June 2011 | HIV Infected Pregnant mother & Child |
| AXSHYA Project | Supported by MAMTA HIMC, N. Delhi | Year June 2012 | T.B |

- Name and address of the Organization:  TI-Office Address: Janhitay Mandal Chandrapur, bypass road Junona Chok Babupeth Chandrapur,444403

- Chief Functionary:  (Project Director-TI: Mr. SS Paliwal)

- Year of establishment:   1992

- Year and month of project initiation: December 2008

- Evaluation team: Ms. Sheeba Rahman (Team Leader  & External Evaluator), Ms.Nida Khan (External Consultant), Naseema Shikh (Accountant DAPCU, Finance Evaluator)

- Time frame: 14th April 2016 to 16th April 2016

Profile of TI

(Information to be captured)

- Target Population Profile: MIGRANTS: Migrants (of the destination)

- Type of Project:  Bridge population:  Bridge population

- Size of Target Group(s): 15000 Migrants

- Sub-Groups and their Size:  High Risk Migrants

- Target Area: TIs’ intervention area stretched in approx. 65 kilometers periphery from the TI office in Chandrapur Maharashtra.

- Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc.

The vision of the key office bearers was not satisfactory only PD involvement from NGO-TI seen and during de-briefing session Project Director (PD)-TI of the organization. The organization’s presence in Chandrapur district at Mahrashtra state was more than 5 years Stakeholders’ opinion could have been taken into considerations in order to get feedback as well as in monitoring the activities. An internal monitoring system was Ppartially witnessed by reviewing minutes of staff-meetings which also attended by PD-TI but the same required to be authentic and as per programme deliverables. At an average one monthly meeting was convened during review period and majority of these meetings were attended by PD. For making the strong voices identification and motivation of stakeholders, efforts could have been undertaken effectively in order to enhance the utilization of services and to create a sustainable impact amongst migrants. However, casual no initiatives witnessed on linking a any of the migrants with benefits through entitlements of various schemes.

II. Organizational Capacity

Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover:

At the time of our evaluations, we were able to meet all the project staff as well as 5 Peer leaders  (PLs) out of  20 mostly comprised  inter migrants. There are eleven source-states’ of migrants included from Bihar and Uttar Pradesh,Chatisgarh,Andra Pradesh,Uttar Pradesh,Odisha,Rajisthan ,Panjab,West Bangal,Jharkhand,Mahrashtra. Identity-cards were issued, at organization level, to staffsbut PE also need ID card for the ease of project intervention . Staffs were given with appointment letters wherein roles and responsibilities were not  spelled-out in Marathi so they are unable to explain JD properly. Following are the staff details:

Staff Details:

| Sl No. | Name of the staff | Designation | Qualification | Working Since with month |
| --- | --- | --- | --- | --- |
| 1 | Dr. S. S. Paliwal | Project Director-TI | D M & S | Dec. 2008 |
| 2 | Birendra Kaithal | Project Manager | MSW | March 2016 |
| 3 | Rita Puradkar | Counselor | MSW | June 2015 |
| 4 | Laxman Bambole | ORW-1 | B. P.Ed | 21.09.2010 |
| 5 | Bhimrao Bambole | ORW-2 | 12th | 01.11.2011 |
| 6 | Bali Bhanarkar | ORW-3 | MSW | 03.06.2013 |
| 7 | Avadhut Gaikwad | ORW-4 | 12th | 01.12.2014 |
| 8 | Sagar C. Gurale | ORW-5 | 12th | 01.04.2014 |
| 9 | Hemant Gedam | ORW-6 | 12th | 01.01.2015 |
| 10 | Shrikant Pattebahadur | ORW-7 | 12th | 05.08.2015 |
| 11 | Vacant Post | ORW-8 | 00 | 00 |
| 12 | Nilam Potdukhekhe | M &E cum Accountant | B.ED | 15.05.2015 |

- Outreach Worker-1: Name:  Laxman Bambole

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1 | Anil K. Meshram | 34 | 12th | 1st Oct. 2011 | Ballarsha |
| 2 | Bhavik D. Padwekar | 40 | B.A. 2 year | 25-Sep-15 | Chandrapur |

- Outreach Worker-2: Name: Bhimrao Bambole

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1. | Jagjiwan Dudhe | 47 | 12th | 1-Jan-15 | Chandrapur |
| 2. | Pankaj Lipate | 21 | 12th | 1-Apr-15 | Chandrapur |

- Outreach Worker-3: Name: Bali Bhanarkar

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1. | Kishor Thakare | 30 | 10th | 18-Jul-13 | Chandrapur |
| 2. | Someshwar Madavi | 31 | 12th | 1-Sep-14 | Chandrapur |
| 3. | Ghanshyam Maskare | 37 | 8th | 1-Apr-14 | Chandrapur |

- Outreach Worker-4: Name: Avadhut Gaikwad

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1 | Akash D. Thamake | 21 | 10th | Apr-15 | Gadchandur |
| 2 | Amol S. Bansod | 30 | B.A. | Mar-15 | Gadchandur |
| 3 | Manik P. Ramteke | 38 | 12th | Jan-15 | Gadchandur |

- Outreach Worker-5: Name: Sagar C. Gurale

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1 | Pradip Budhhaji Telang | 22 | 12th | 15-Oct | Chandrapur |

- Outreach Worker-6: Name: Shrikant Pattebahadur

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1 | Kishor Gorselwar | 24 | 12th | 16-Jan | Chandrapur |
| 2 | Sanjay Meshram | 22 | 10th | 16-Jan | Chandrapur |

- Outreach Worker-7: Name: Hemant Gedam

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1 | Sunil Soyam | 23 | 10th | 15-Aug | Chandrapur |
| 2 | Ranjit Sonule | 24 | 12th | 16-Jan | Chandrapur |
| 3 | Rohit Choudhary | 24 | BA | 04-Jan | Chandrapur |

- Outreach Worker-8: Name: - Currently Vacant from March 16

| Sl. No | Name of PL | Age in years | Qualification | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- |
| 1 | Alim Pathan | 31 | 12th | Jun-14 | Ballrsha |
| 2 | Dipak Warma | 33 | 10th | Aug-15 | Ballrsha |
| 3 | Nitesh Meshram | 25 | B.A. | Feb-15 | Gadchandur |

Capacity building training: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

Trainings were happened by MSACS/TSU since 2011 as per the interaction with the TI-team and available record.   Technical knowledge is needed for good intervention all staff needed modular training on migrants.

| Sl.No. | Name of staff | Designation | Training given by | Content |
| --- | --- | --- | --- | --- |
| 1. | S. S. Paliwal | PD | MSACS | CNA |
| 2 | Birendra Kaithal | PM | NGO | Orientation |
| 3 | Rita Puradkar | Counselor | NGO | Orientation |
| 4 | Laxman Bambole | ORW | NGO | Orientation |
| 5 | Bhimrao Bambole | ORW | NGO | Orientation |
| 6 | Bali Bhanarkar | ORW | NGO | Orientation |
| 7 | Avadhut Gaikwad | ORW | NGO | Orientation |
| 8 | Sagar C. Gurale | ORW | NGO | Orientation |
| 9 | Hemant Gedam | ORW | NGO | Orientation |
| 10 | Shrikant Pattebahadur | ORW | NGO | Orientation |
| 12 | Nilam Potdukhe | M &E cum Accountant | NGO | Orientation |

Infrastructure of the organization:

TI Office is located at bypass road Junona Chok Babupeth Chandrapur only one site is  accessible easily  from TI office , other  site is 10 to 65 kms away from TI office.

The TI office including  PD home as well as small hospital of PD –TI running from same building  and  same premises. One big room is used for PM,M&E & ORW another small counseling room, wash room is  used by TI staff DIC is not available in office premisis. Internet facilities was available. One computer available in the Office.

There are two DICs of the TI one of the distant intervening area named Nadafata and second one is Lakhamapur but Nadafata DIC is closed after 31 st March 15 due to low footfall. The TI-office cum DIC is very essential in Babupeth Chandrapur, having enough space for working of the team. Assets’ records were available and duly coded as well but the same was still to be verified periodically.

4.  Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting an feedback mechanism, dissemination and sharing of the reports and documents for technical

inputs if any.

Info sharing for translating the planned activities towards implementation as well as having feed-back thereon was not well evident through documents but various services need to be the part of plan for tracking the proper service delivery.Documents were available on treatment along with referral (slips) and doctor’s prescriptions’ foil for organization with each case history but in some slips . Measurable plans after technical inputs for achieving quantified targets need to be incorporated through various activities intended. There was lot of scope for improvement of different hierarchal positions of the staff. Moreover, Counselor’s records were maintained ,Further, in the presence of review mechanisms with this intervention, numerological targets were missing to be translated from upper hierarchy to the grassroots staffs. These gaps could have been easily be fulfilled by planning on-site mentoring either by SACS (TSU or else) and senior management staff of intervention, Presently PCM is not continue. Though the intervention adheres to the SACS protocols in terms of using NACO formats but it had further scope to strengthen the same in order to add all the requisite information. The project has formulated Project Management Committee (PMC) on  2011 and only two minutes were recorded (for 10th September 2011, 10th November  2011) but representation of stakeholders/migrants was extremely less (Only3 stakeholders  without PLs). There was scope to improve for quality documentation, hence protocol based mentoring was felt essential at this junction of time.

III. Program Deliverables

Outreach

1.  Line listing of the HRG by category.

2.  Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

3.  Registration of truckers from 2 service sources i.e. STI clinics and counseling.

4.  Micro planning in place and the same is reflected in Quality and documentation.

5.  Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

6.  Outreach planning - quality, documentation and reflection in implementation

7.  PE: HRG ratio, PE: migrants/truckers

8.  Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

9.  Documentation of the peer education

10. Quality of peer education- messages, skills and reflection in the community

11. Supervision- mechanism, process, follow-up in action taken etc

The project has been assigned with the target of 15000 migrants to intervene while 84117(Male-15017,Female-3495) migrants were registered  from 2008 to 2016 out of 11616 registered High risk migrants  only  9147(60%) Target   is having high risk behavior,and it felt that in Chandrapur assigned or selected sites is very scattered and small(40-50 Migrants)pockets of construction labors due to wrong selection ,TI staff is not got  needed result it is suggested  that reconsider the site selection of JM chandrapur

A total appointed 19(sanctioned 20) PLs were working to cater peer education related activities and the team could met with 05 one of them had rather well versed on desired communication skills but they all are from Maharashtra only not from source distrct  or  from contactors or brokers they observed doing documentation or having plans. Penis-model for condom demonstration was available with met PLs. However, in BCC sessions, there were contents on mode of transmission, safe sex practices, risky behavior, removal of myths and mis-conceptions etc. The required ratio of PL: migrants were rather within norms. During mid-media, a range of IEC (in Marahi) were also used which among many others included leaflets, brochures, booklets, flip-charts etc. and nukkad-nataks and there also happened condom demonstration, STI/ICTC referrals along with orations by staffs/PLs and by a few the resource persons.

IV. Services

1.  Availability of STI services - mode of delivery, adequacy to the needs of the community.

2.  Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

3.  In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

4.  Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centers.

5.  Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

6.  Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

7.  No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

8.  No. of Needles / Syringes distributed through outreach / DIC.

9.  Information on linkages for ICTC, DOT, ART, STI clinics.

10. Referrals and follows up

Availability of STI services:

STI services are mainly catered by one male PPP doctor whose details are underneath:

Details of PPP doctor:

| Sl. No. | Name of the Doctor | Allopath/non-allopath | Received training on Syndromic Management from SACS/TSU | Letter of Understanding (LoU) signed: Yes/No |
| --- | --- | --- | --- | --- |
| 1. | Dr. S. S. Paliwal | Allopath (D.M. & S) | Yes | Yes |
| 2. | Dr. Sandip Shende | Non allopath (BAMS) | No | Yes |
| 3. | Dr.Kartikesh N.Gokhare | DHMS | Yes | Yes |

Quality of the services and treatment in the service provisioning:

Maximum treatment done by Dr.Kartikesh N.Gokhare during discussion with Dr.Kartikesh N.Gokhare he is not confident to explain symptomatic case management needs explanatory training.

Service provisioning in context of STI treatment was observed being done through govt. referral and  PPP model (male and female )through camp and PPP clinic. In addition to ICTCs of Civil  Government Hospital Chandrapur and Rural Hospital Balrshah,Gadchadur,Gondpipery ICTC for HIV-testing while Two PPP doctor(Dr.Shindey is BAMS and Dr.Paliwal is Diploma in medical and surgery who is PD of TI also) observed working for the intervention.

Documentation

Documentation done but there had lot of scope for improvement. However, counseling register and referral register, STD register, STI drug stock register, network clinic form, etc. found maintained and Counselor could not properly explain the same (as was explained by PM).

Availability of Condoms- Type of distribution channel, accessibility, adequacy, No of condoms distributed etc:

Outreach workers and peer leaders not observed distributing free condoms. Free condoms being used in the field for demo and re-demo purposes. CSM is being done by the TI. The main channel of condom sail was through PLs condom outlets (non-traditional). As per the record CSM balance as on 14th 2016 was 540.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Community participation was reflected through a 32 events (11 congregation event and 21 street pays) total participants 1485(9.9 %) but committees not activated yet.Even Project Management Committee  formulated  in 2011 only two  meetings were held in 2011 but after 2011 PMC was not continue.

VI. Linkages

1.  Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

2.  Percentages of HRGs tested in ICTC and gap between referred and tested.

3.  Support system developed with various stakeholders and involvement of various stakeholders in the project.

Following linkages observed being used by the TI:

- ICTC/VDRL/STI/TB – General Hospital, Chandrapur

- ICTC/ VDRL/STI/TB/ART –

- General Hospital, Chandrapur

- Bilt ART Centre, Ballarsha

- ICTC – ICTC1 & 2 GH Chandrapur, RH Ballarsha, RH Gadchandur, RH Gondpipari

Visit   done of ICTC/STI/TB/ART –Civil Hospital, Chandrapur

Team able to meet with Ms.Rakhi Deshmukh (Counselor-STI)Mr.Rakesh duryodan,Ms.Sharda Lokhande (ICTC Counselor) Shalini(LT),Mr.Kiran Borkar(ART counselor),Data manager Mr. Vilas Bobade,In DAPCU-DPM-Mr.Sumant Pangantiwar,DS-Mr.Niranjan,  Monthly coordination meeting was regular, coordination with all services is quit supportive.

At a glance, linkage-wise services (along with certain relevant indicators) could be depicted as follows:

| Indicator | Period April 15 to March 15 |
| --- | --- |
| Target allocated | 15000 |
| Total registration | 11616 |
| Active population till 2016 | 8265 |
| Date of Project Management Committee (PMC) formulated | 10.09.2011 yet not continue |
| No. of PMC meetings | 0 |
| No. of congregation points proposed | - |
| No. of congregation points catered | 74 |
| No. of congregation events in last one year (April 2015 to March 2016) | 11 |
| Mid media events in last one year (April 2015 to March 2016) | 21 |
| No. of condom outlets (traditional/non-traditional) | 101 Non Traditional |
| No. of Free condom used only for demo- and re-demo | 2975 |
| No. of outlets | 101 |
| CSM Distribution in last one year | 11100 |
| Condom Balance as on date 31.03.2016 (free) Exclusively being used for Demo & Re-demo | 250 |
| Condom Balance as on 31st March 2016 (CSM) (N.B.: Popular brand name- “Thrill”) | 540 |
| Total No. of PLs | 19 |
| No. of PLs from source district (belonging to UP & Bihar) | 01 |
| No. of sessions conducted by ORWs in last twelve month (April 15 to March 16) | 1508 |
| ORW Coverage | 17004 |
| No. of sessions organized by PLs in last twelve month (April 15 to March 16) | 4144 |
| No. of PLs’ sessions supervised by ORWs | 366 |
| PL Coverage | 48398 |
| No. of Counseling Session at Clinic/Site/DIC | 206 |
| Mid-media events in April. 15 to June 15 months | 01 |
| Mid-media events in July 15 to Sept. 15 months | 03 |
| Mid-media events in Oct. 15 to Dec 15 months | 18 |
| Mid-media events in Jan 16 to March16 months | 11 |
| No. of suspected TB cases linked RNTCP | 49 |
| Total STI cases diagnosed during review period | 658 |
| Total STI cases treated during review period | 658 |
| Total STI cases followed-up during review period | 658 |
| No. of STI cases tested ICTC during review period | 636 |
| Total ICTC April 15 to March 16 | 2992 |
| Total No. of HIV positives during April 2015 to March 2016 | 11 |
| Total No. of HIV positives linked to ART during January 2015 to December 2015 | 11 |
| No. of +ves in follow-ups with last CD4 count | 09 |
| Total No. of HIV positives (Cumulative) | 68 |
| No. of +ves migrated and not in reach (cumulative) | 49 |

VII. Financial systems and procedures

Systems of planning:

The received fund utilized  equal or below as per the budget approved. All expenditure approved

through concern authority.

Systems of payments-

From our verification of books of accounts and other related document we found that, all payments are made through account payee/RTGS method. All supporting documents approved by concern authority also. Found the cash payment below of Rs. 5000/- on the basis urgency. No other cash transactions above Rs.5000/- than a cash of Rs. 6300/- for Professional Tax only.

Systems of  procurement-

- Insurance for staff.

- AMC computers.

Group Insurance for employees are not implement. AMC of Computers are done. Procurement Process has been processed through quotation.

Systems of documentation-

A separate Bank account is operated for said project with two signatory authority

at branch Chandrapur of Syndicate Bank. All Bank Reconciliation Statement available. All SOE & UC submitted. Bills and vouchers have been examined and found in order which is subsequently recorded  in tally software version 7.2.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal,  Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

Absent during evaluation

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

Presently working Counselor is MSW as per NACO norms recently appointed in other project will join on May 2016 onwards position will vacant but still getting herself acclimatized for the project but lot more is to be understood by her in order to properly conceptualize the project protocol. TI and past Counselor’s documented supervision/follow-up was also invisible. she is clear about  risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs etc. So far as maintenance and updating of data and registers, efforts have been made but were inadequate. It will recommend for male counselor is more effective for this area as per PL suggestion.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.

For ANM, adequate abscess management skills.

Not applicable

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc.

Total 8 ORW  presently working  in TI and  The project’s ORWs still need to be versed properly about target on various indicators for their PLs, outreach plan, registration of high risk migrants selection criteria of PLs supportive supervision of PL sessions, field level action based on review meetings etc. As per the available records timeliness was followed for submission of their reports. By interviewing respondents at various hotspots, it was reflected that ORWs have got their rapport.

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

VIII f. Peer educators in IDU TI

Prioritization  of  hotspots,  condom  demonstration,  importance  of  RMC  and  ICTC  testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

Not applicable for this TI as evaluated.

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritize the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

One  peers represent the source states (Madhya Pradesh) from where maximum migrants of the area belong to and they are rather able to prioritize the networks/locations where migrants work/reside/access high risk activities. Only one of the peers was able to demonstrate condoms but observed dependent for planning outreach.  Five PLs (out of 20) had met during the entire span of the project evaluations. Three of them were having limited familiarity with the project while one was observed rather versed on intervening spots, STI screening ,ICTC, skills on condom demonstration as well as knowledge  about condom depots, symptoms of STI, issues related to treatment of TB and other project relevant service facilities.

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

Not applicable for this TI as evaluated.

VIII i. M&E officer

Whether the M&E officer (FSW and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

Exclusive M&E position was sanctioned as per the typology but at majority of occasions she has given the gesture of his limited ability of providing with analytical data relevant to the programme. However, she, at considerable extent, able in providing key information about various indicators reported in TI and STI CMIS reports.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs.  Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

Not applicable for this TI as evaluated.

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs/PLs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

Through our interactions, all of the ORWs rather understood the number of outreach sessions conducted by ORWs' session plans were shared to PLs to some extent but below 8% were attended..Total 4144 sessions done by PLs 331 attended by ORW. However authentic data were still to be captured by ORWs' for their records.Total 4144 sessions done by PLs 331 attended by ORW.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

Overall service uptake, its quality in the project still need to be as per performance indicators but some of the met migrants as interacted were satisfied by the intervention in terms of message delivery, staffs’ attitude as well as linking towards service uptake.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

The community participation was not  visible in context of migrants, married and others which become possible due to mobilizing their direct stakeholders. No doubt, concerns of migrants were captured through meetings but they were not as such involved in planning process. Advocacy efforts were undertaken to some extent but relevant documentations were improper. The benefits of  community’s involvement in monitoring the project activities was yet to be understood by the project team, rather their migrants’ stakeholders- owners/managers had made track on intervention activities who were observed supporting at large.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes.  Method of demand calculation, Female condom programme if any,

The project has 101 number of non-traditional condom outlet which were functional to make the accesses at all the intervening areas. Initially the project made non-traditional outlets Further, in a migrant intervention where condom social marketing (CSM) lead to project sustainability by health seeking behavior of the audience targeted, randomized  marketing/distribution might be avoided through condom depot channels or through PL/ORW and in message delivery systems same could have been incorporated measurably whilst doing BCC by the project team. Female condoms were neither procured nor provisioned through any TI-networks.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

Though the project has not formulated Project Management Committee (PMC) but was able to involve only a few of the potential stakeholders/migrants in some extend in the program activities which is not documented properly. Systematic plan for advocacy was still wanting. However, each of the two ORWs, at their level, doing advocacies and were recorded by themselves. In addition to these advocacy efforts.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

The project had not yet to provide any social protection schemes/ welfare schemes/social entitlements.

XV. Best Practices if any

None of the practices were identified as best ones.