Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

- Background of Project and Organisation:

Noble Shikshan Sanstha Establish is a developmental organization working on public health issues formalized it’s entity as a nonprofit making secular organisation to combat the situation. As an organisation started with since last 28 years. Society was registered 	under SR Act Society Registration Act, 1860. NSS  is implementing  HIV related projects in partnership with MSACS in Chandrapur districts, . The organisation is working with the support of national, state and corporate funding’s. The organization is implementing targeted intervention (TI) project on (destination) migrants in the district of Chandrapur in the state of Maharashtra as one the partners of Maharshtra State AIDS Control Society (MSACS) since December 2012. Majority of project beneficiaries of this migrant TI belonged to the states of Bihar and Chatisgarh,Andra Pradesh,Uttar Pradesh,Odisha,Rajisthan,Panjab,West,Bangal,Jharkhand,Mahrashtra,MadhyaPradesh,Karnataka,Karela,Gujrat,GOA,Tamilnadu,Delhi,Utranchal HRG migrants (HRGM).

| Name of the Project | Funded By | Year | Working Area |
| --- | --- | --- | --- |
| TI F.S.W. Project, Chandrapur | MSACS, Mumbai | 2003 | Chandrapur |
| TI Aashray Trukers Project, Chandrapur | MSACS, Mumbai | 2010 | Chandrapur |
| TI Migrant Project, Chandrapur | MSACS, Mumbai | 2012 | Chandrapur |
| Link Worker Scheme, Wardha | MSACS, Mumbai | 2010 | Wardha, District |
| PPTCT Wardha District | IL&FS Education Technology Services Ltd., Noida | 2010 To End of Project 30-11-2015 | Wardha, District |

- Name and address of the Organization:  TI-Office Address: Nobel Shikshan Sansthan Chandrapur,  C/O Dr Mahesh Bhandekar near balagi sabha greh  balaji ward Chandrapur,444403

- Chief Functionary:  (Project Director-TI: Mr.Praveen Krushnarao Hiyare)

- Year of establishment:   1988

- Year and month of project initiation: December 2012

- Evaluation team: Ms. Sheeba Rahman (Team Leader  & External Evaluator), Ms.Nida Khan (External Consultant), Naseema Shikh (Accountant DAPCU, Finance Evaluator)

- Time frame: 17th April 2016 to 19th April 2016

Profile of TI

(Information to be captured)

- Target Population Profile: MIGRANTS (Destination)

- Type of Project:  Bridge population:  Bridge population

- Size of Target Group(s): 20000 Migrants

- Sub-Groups and their Size:  High Risk Migrants

- Target Area: TIs’ intervention area stretched in approx. 50 (Varoda) kilometers periphery from the TI office in Chandrapur Maharashtra.

- Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc.

During the visit by the evaluation team, it was observed that the key office bearer of the TI had a fair understanding of the project and its implementation. They had a vision about the project, its components and the impact and achievements However, M&E support all the program. The NGO team is partially clear about networking and advocacy with the community. Monitoring and supervision need to be more strong. The role of the Project Director was found satisfactory; moreover the PD was present at the time of the visit for interaction. The organization’s presence in Chandrapur district at Mahrashtra state was more than 2 years Stakeholders’ opinion could have been taken into considerations in order to get feedback as well as in monitoring the activities. An internal monitoring system was partially witnessed by reviewing minutes of staff-meetings which also attended by PD-TI but the same required to be authentic and as per programme deliverables. At an average one monthly meeting was convened during review period and majority of these meetings were attended by PD. For making the strong voices identification and motivation of stakeholders, efforts could have been undertaken effectively in order to enhance the utilization of services and to create a sustainable impact amongst migrants. However, casual no initiatives witnessed on linking a any of the migrants with benefits through entitlements of various schemes.

II. Organizational Capacity

Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover:

The staff of the project has been placed as per the proposal requirements, only two staff member dropouts which had been replaced within the given timeframe, the staff has positive outlook but the energy levels of the staff need to be boosted so that they become very active in the fields. The overall understanding and commitment towards the project was found satisfactory. They are technically sound and have guidance and direction for their project.

At the time of our evaluations, we were able to meet all the project staff as well as 15 Peer leaders  (PLs) out of  26 mostly comprised  inter migrants. There are 20 source-states’ of migrants included from Bihar and Chatisgarh,Andra Pradesh,Uttar Pradesh,Odisha,Rajisthan ,Panjab,West,Bangal,Jharkhand,Mahrashtra,MadhyaPradesh,Karnataka,Karela,Gujrat,GOA,Tamilnadu,Delhi,Utranchal. Identity-cards were issued, at organization level, to staffs but PE also need ID card for the ease of project intervention . Staffs were given with appointment letters wherein roles and responsibilities were not  spelled-out in Marathi so they are unable to explain JD properly. Following are the staff details:

Staff Details:

| Sl No. | Name of the staff | Designation | Qualification | Working Since with month |
| --- | --- | --- | --- | --- |
| 1 | Mr.Swapnil D. Martiwar | Project Manager | MSW | 2 years10Months |
| 2 | Pravin C. Nair | Counselor | MSW | 2 years10Months |
| 3 | Madhuri D. Dongare | M&ECum Accountant | MCom | 3Years 3Months |
| 4 | Ajay P. Gajjalwar | ORW | 10th | 3 Years3Months |
| 5 | Padmakar K. Solankar | ORW | 12th | 3 Years3Months |
| 6 | Sagar Ghate | ORW | B.Com | 7 Months |
| 8 | Rubina Sheikh | ORW | 12th | 6 Months |
| 9 | Sachin M. Pawde | ORW | 12th | 7 Months |
| 10 | Arun N. Shende | ORW | BSW | 2 Years |
| 11 | Gaurav R. Chitmalwar | ORW | 12th | 2 Years |
| 12 | Shaban F. Sheikh | ORW | 12th | 2 Years |
| 13 | Ganesh B. Nibrad | ORW | M.A. | 2 Years |
| 14 | Preeti R. Chaudhari | ORW | 12th | 2 years |

Outreach Worker-1: Name: Ajay Gajjalwar

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Ravi S. Durge | 25 | 10th | 770 | 2-4-2015 | VInar Ispat Company |
| 2 | Vijay jalpath Kondawar | 24 | 10th | 770 | 1-6-2014 | MIDC Datala |

Outreach Worker-2: Name: Padmakar Solankar

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Vishal Bawne | 26 | 12th | 770 | 1June2015 | Amarai Ward |
| 2. | Parshuram M. Dhulgunde | 26 | 12th | 770 | 1November 2015 | Labour Colony |
| 3. | Atul M. Yergude | 25 | B.Com | 770 | 1June2014 | Nakoda |

Outreach Worker-3: Name: Rubina Sheikh

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Sushil A. Modak | 28 | 10th | 770 | 1Sep2015 | Tadali |
| 2. | Shubham Hedaoo | 24 | 12th | 770 | 2April2015 | Dharewal Quarter Tadali |
| 3. | Harun Yusuf Sheikh | 28 | 10th | 770 | 1June2015 | Bhadravati |

Outreach Worker-4: Name: Sagar Ghate

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Priti M. Padmanabhan | 30 | B.A. | 770 | 1Oct-2014 | Gupta Power Plant Usegaon |
| 2 | Shriniwas L. Dampelli | 30 | 10th | 770 | 1April 2015 | Loyds Metal Ghugus |
| 3 | Sanjay M. Nannaware | 37 | B.A. | 770 | 1April 2014 | DNR, Sapara Company Ghugus |

Outreach Worker-5: Name: Sachin M. Pawde

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Samir N. Bakal | 23 | 12th | 770 | 1St Nov2015 | Durgapur |
| 2 | Shubham L. Govindwar | 21 | 12th | 770 | st Mar2015 | Lalpeth |
| 3 | Sachin B. Ruyarkar | 26 | B.A. | 770 | 1April2014 | SEW Durgapur |

Outreach Worker-6: Name: Gaurav R. Chitmalwar

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Vishal dilip Allyadwar | 25 | 12th | 770 | 1June2015 | Padmapur |
| 2 | Sukshma Bambode | 28 | B.A. | 770 | 1June2014 | Lalpeth |

Outreach Worker-7: Name: Arun Shende

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Bharti S. Rane | 28 | 12th | 770 | 1June2015 | Shree Omty Company |
| 2 | Rameshwar S. Dhabekar | 23 | 12th | 770 | 1July2014 | Vimala Company |
| 3 | Atish M. nagdevate | 22 | 10th | 770 | 1July2014 | Padoli |

- Outreach Worker-8: Name: - Shabana Sheikh

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Farukh sheikh | 30 | 10th | 770 | 1April2014 | Sasti Gauri Deep |
| 2 | Rahim Pathan | 30 | 10th | 770 | 1March2015 | Chunala, Bamni, Chanakha |

Outreach Worker-9: Name: - Ganesh Nibrad

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Mangesh Pusdekar | 20 | 12th | 770 | 1April2014 | Gitti Khadan panjurni |
| 2 | Akash Gopal salam | 25 | 10th | 770 | 1June2014 | WArdha Power Plant |

Outreach Worker-9: Name: - Priti Chaudhari

| Sl. No | Name of PL | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Ramesh D. Chaudhari | 38 | 12th | 770 | 1April2014 | Mul |
| 2 | Varsh H. Selote | 30 | 12th | 770 | 1June201 | MIDC Maregaon |

Capacity building training: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

Trainings were happened by MSACS/TSU since 2011 as per the interaction with the TI-team and available record.   Technical knowledge is needed for good intervention all staff needed modular training on migrants.

| Sl.No. | Name of staff | Designation | Training given by | Content |
| --- | --- | --- | --- | --- |
| 1. | Mr. Swapnil D. martiwar | Project Manager | MSACS, Mumbai | Sims Training |
| 2 | Madhuri D. Dongar | M&E cum Accountant | MSACS, Mumbai | Sims Training |
| 3 | Mr. Swapnil D. martiwar | Project Manager | MSACS, Mumbai | Induction Training |
| 4 | Madhuri D. Dongar | M&E cum Accountant | MSACS, Mumbai | Induction Training |
| 5 | Pravin C. nair | Consellor | MSACS, Mumbai | Induction Training |
| 6 | Mr. Swapnil D. martiwar | Project Manager | MSACS, Mumbai | Induction Training |
| 7 | Mr. Swapnil D. martiwar | Project Manager | MSACS, Mumbai | MSDS Formates Training |
| 8 | Madhuri D. Dongar | M&E cum Accountant | MSACS, Mumbai | MSDS Formates Training |

Infrastructure of the organization:

The NGO Office was located at near balagi sabha greh  balaji ward Chandrapur. TI Office cum DIC is central location of Chandrapur city. Very near from  ICTC, Govt. Hospital, ART Centre  The office has a DIC, Clinic and one staff room within its premises. There is computer, tables and chairs are from TI project budget and other equipments provided under the project. Informative posters (printed and handmade) about HIV/AIDS and other government schemes for the migrants are displayed on the walls.  Resource mapping charts are being also being displayed. Assets’ records were available and duly coded as well but the same was still to be verified periodically.

NSS second DIC is situated at C/o, Mr. Raju Mashirkar Amrai Ward, Ghugus. from which NSS are able to cover the migrant population of ACC Cement estimated  670 Migrants  third DIC is situated at c/o. Mr. Ishwar Akhare,Tadali, Chandrapur which is very near to MIDC Tadali & Dhariwal company.

4.  Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting an feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

Although  files and records have been maintained as per the guidelines of NACO. The NGO sends the Report to SACS and TSU as per the timelines and shares the report with PD but selection of sites for high risk migrants registration and  selection of PL will need to focus by PO/TSU/MSACS for technical inputs.

Various services need to be the part of plan for tracking the proper service delivery.Documents were available on treatment along with referral (slips) and doctor’s prescriptions. Measurable plans after technical inputs for achieving quantified targets need to be incorporated through various activities intended. There was lot of scope for improvement of different hierarchal positions ie.PM,Counselor,and ORW . Moreover, Counselor’s records were maintained ,Further, in the presence of review mechanisms with this intervention, numerological targets were missing to be translated from upper hierarchy to the grassroots staffs. Presently PCM is not continue. Though the intervention adheres to the SACS protocols in terms of using NACO formats but it had further scope to strengthen the same in order to add all the requisite information.

III. Program Deliverables

Outreach

1.  Line listing of the HRG by category.

2.  Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

3.  Registration of truckers from 2 service sources i.e. STI clinics and counseling.

4.  Micro planning in place and the same is reflected in Quality and documentation.

5.  Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

6.  Outreach planning - quality, documentation and reflection in implementation

7.  PE: HRG ratio, PE: migrants/truckers

8.  Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

9.  Documentation of the peer education

10. Quality of peer education- messages, skills and reflection in the community

11. Supervision- mechanism, process, follow-up in action taken etc

The project has been assigned with the target of 20000 migrants to intervene while 20161(Male-12081,Female-1969,dropedout-6011) migrants were registered  from 2008 to 2016.

A total appointed 26(sanctioned 26) PLs  selection was not properly done due to lack of technical knowledge

The  evaluation team could met with 15  of them had rather versed on desired communication skills but they all are from Maharashtra only not from source district  or  from contactors or brokers they observed doing documentation or having plans.,need to reselection of PL needed, Penis-model for condom demonstration was unavailable with met PLs. However, in BCC sessions, there were contents on mode of transmission, safe sex practices, risky behavior, removal of myths and mis-conceptions etc. The required ratio of PL: migrants were rather within norms. During mid-media, a range of IEC (in Marahi) were also used which among many others included leaflets, brochures, booklets, flip-charts etc. and nukkad-nataks and there also happened condom demonstration, STI/ICTC referrals along with orations by staffs/PLs and by a few the resource persons.

IV. Services

1.  Availability of STI services - mode of delivery, adequacy to the needs of the community.

2.  Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

3.  In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

4.  Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centers.

5.  Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

6.  Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

7.  No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

8.  No. of Needles / Syringes distributed through outreach / DIC.

9.  Information on linkages for ICTC, DOT, ART, STI clinics.

10. Referrals and follows up

Availability of STI services:

STI services are mainly catered by one male PPP doctor whose details are underneath:

Details of PPP doctor:

| Sl. No. | Name of the Doctor | Allopath/non-allopath | Received training on Syndromic Management from SACS/TSU | Letter of Understanding (LOU) signed: Yes/No |
| --- | --- | --- | --- | --- |
| 1. | Dr. Pawan Markandewar | BAMS | No | Yes |
| 2. | Dr. Pankaj Yerne | BAMS | No | Yes |

Quality of the services and treatment in the service provisioning:

Maximum treatment done by Dr.Pawan Markhandewal,Dr.Pankaj Virney during discussion with Dr.Pawan Markhandewal,Dr.Pankaj Virney he is confident to explain symptomatic case management.

Service provisioning in context of STI treatment was observed being done through govt. referral and  PPP model (male and female )through camp and PPP clinic. In addition to ICTCs of Civil  Government Hospital Chandrapur andBadrawati ICTC,Varoda ICTC,Mul ICTC,Rajura ICTC for HIV-testing while 2 PPP doctorDr. Dr.Pawan Markhandewal Dr.Pankaj Virney, is BAMS observed working for the intervention.

Documentation

All files and records have been maintained as per the guidelines of NACO. The NGO sends the Report to SACS and TSU as per the timelines and shares the report with PD for his technical inputs. However, counseling register and referral register, STD register, STI drug stock register, network clinic form, etc. found maintained.but in master sheet riskey behavior column not filled by some ORWs it is very serious issue for PO-TSU due to less technical inputs of high risk migrants registration process need to focus and related documants need to focus by TSU-PO/MSACS.

Availability of Condoms- Type of distribution channel, accessibility, adequacy, No of condoms distributed etc:

Outreach workers and peer leaders not observed distributing free condoms. Free condoms being used in the field for demo and re-demo purposes. CSM is being done by the TI. The main channel of condom sail was through PLs condom outlets (non-traditional). As per the record CSM balance as on 17th 2016 was 800.

Condom Details:

| Demand(April 2015 to March 2016) | Free Distribution(April 2015 to March 2016) | Distribution CSM(April 2015 to March 2016) |
| --- | --- | --- |
| NA | 0 only demo | 31012 |

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Community participation was reflected through a 54 events (07 congregation event and 22 street

pays, Demand generation activity-22,Poster Exibition-2) total participants 4094 but committees

not activated yet.PMC not initiated yet .

VI. Linkages

1.  Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

2.  Percentages of HRGs tested in ICTC and gap between referred and tested.

3.  Support system developed with various stakeholders and involvement of various stakeholders in the project.

Following linkages observed being used by the TI:

- ICTC/VDRL/STI/TB /ART – General Hospital, Chandrapur

- ICTC/ VDRL/STI/TB/ – i.) RH Rural Hospital, Rajura

iii) RH Rural Hospital,Bhadravati

- ICTC – Sub District Hospital, Warora

- ICTC - Sub District Hospital, Mul

Visit   done of ICTC/STI/TB/ART –Civil Hospital, Chandrapur

Team able to meet with Ms.Rakhi Deshmukh (Counselor-STI)Mr.Rakesh duryodan,Ms.Sharda Lokhande (ICTC Counselor) Shalini(LT),Mr.Kiran Borkar(ART counselor),Data manager Mr. Vilas Bobade,In DAPCU-DPM-Mr.Sumant Pangantiwar,DS-Mr.Niranjan,  Monthly coordination meeting was regular, coordination with all services is quit supportive.

At a glance, linkage-wise services (along with certain relevant indicators) could be depicted as follows:

| Indicator | Period April 15 to March 16 |
| --- | --- |
| Target allocated | 20000 |
| Total registration | 20161 |
| Active population till 2016 | 20161 |
| Date of Project Management Committee (PMC) formulated | PMC not formed |
| No. of PMC meetings | PMC not formed |
| No. of congregation points proposed | 170 |
| No. of congregation points catered | 170 |
| No. of congregation events in last one year (April 2015 to March 2016) | 7 |
| Mid media events in last one year (April 2015 to March 2016) | 53 |
| No. of condom outlets (traditional/non-traditional) | 93 |
| No. of Free condom used only for demo- and re-demo |  |
| No. of outlets | 93 |
| CSM Distribution in last one year | 31012 |
| Condom Balance as on date 31.03.2016 (free) Exclusively being used for Demo & Re-demo | 1900 |
| Condom Balance as on 31stMarch 2016 (CSM) (N.B.: Popular brand name- “Thrill”) | 1500 |
| Total No. of PLs | 26 |
| No. of PLs from source district (belonging to UP & Bihar) | 0 |
| No. of sessions conducted by ORWs in last twelve month (April 15 to March 16) | 1169 |
| ORW Coverage | 13905 |
| No. of sessions organized by PLs in last twelve month (April 15 to March 16) | 5680 |
| No. of PLs’ sessions supervised by ORWs | 528 |
| PL Coverage | 58856 |
| No. of Counseling Session at Clinic/Site/DIC | 8126 |
| Mid-media events in April. 15 to June 15 months | 12 |
| Mid-media events in July 15 to Sept. 15 months | 9 |
| Mid-media events in Oct. 15 to Dec 15 months | 18 |
| Mid-media events in Jan 16 to March16 months | 14 |
| No. of suspected TB cases linked RNTCP | 0 |
| Total STI cases diagnosed during review period | 1383 |
| Total STI cases treated during review period | 1383 |
| Total STI cases followed-up during review period | 779 |
| No. of STI cases tested ICTC during review period | 1383 |
| Total ICTC April 15 to March 16 | 6437 |
| Total No. of HIV positives during April 2015 to March 2016 | 10 |
| Total No. of HIV positives linked to ART during January 2015 to December 2015 | 8 |
| No. of +ves in follow-ups with last CD4 count | 27 |
| Total No. of HIV positives (Cumulative) | 33 |
| No. of +ves migrated and not in reach (cumulative) | 6 |
| Total No. of cumulated HIV positives currently linked to ART | 31 |
| Any other linkage | 0 |

| UID | Date of HIV Test | Name of ICTC | PID No | Date of Pre ART registration | Baseline CD 4 test data | Baseline CD 4 Count | Whether put on ART or not | Reason for not getting ART |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 27/21/008/00/G/10162 | 18-2-2013 | CHandrapur | CH/001/13/1542 | 1-9-2014 | 1-9-2014 | 218 | YES |  |
| 27/21/008/00/G/10077 | 7-2-2013 | CHandrapur | CH/001/13/1541 | 10-1-2014 | 10-1-2014 | 97 | YES | Transfer to Nagpur ATR Centre(IGME Centre Nagpur 22-9-2014) |
| 27/21/008/00/G/13865 | 8-7-2017 | Chandrapur | CH/202/13/2203 | 15-7-2013 | 15-7-2013 | 415 | No | Migrant Drop Out with in 4-5 time follow up 30-3-2015 |
| 27/21/008/00/G/15257 | 27/8/2013 | Bhadravati | CH/202/13/2861 | 2-9-2013 | 2-9-2013 | 319 | No |  |
| 27/21/008/00/G/15497 | 10-9-2013 | Bhadravati | CH/202/13/2974 | 11-9-2013 | 11-9-2013 | 58 | YES |  |
| 27/21/008/00/G/16609 | 28-10-2013 | Chandrapur | CH/001/13/11240 | 28-10-2013 | 28-10-2013 | 601 | No | Not Ready to come for CD4 testing |
| 27/21/008/00/G/17616 | 28-11-2013 | Chandrapur | CH/001/13/12333 | 28-11-2013 | 28-11-2013 | 274 | YES | Not Ready to come for CD4 testing |
| 27/21/008/00/G/22161 | 22-4-2014 | Bhadravati | CH/200/14/1573 | 28-4-2014 | 28-4-2014 | 67 | YEs |  |
| 27/21/008/00/G/25025 | 10-6-2014 | Warora | CH/002/14/2001 | 1/12/2014 | 1/12/2014 | 235 | YES | Transfer to Gadchiroli |
| 27-21-008-00/G/26949 | 7-7-2014 | Bhadravati | CH/202/14/2508 | 8/7/2014 | 8/7/2014 | 224 | YES |  |
| 27/21/008/00/G/26950 | 7-7-2014 | Bhadravati | CH/202/14/2509 | 8/7/2014 | 8/7/2014 | 600 | No |  |
| 27/21/008/00/G/32314 | 20-10-2014 | Bhadravati | CH/202/14/13509 | 20-10-2014 | 20-10-2014 | 263 | YES |  |
| 27/21/008/00/G/32286 | 20-10-2014 | Bhadravati | CH/202/14/13508 | 20-10-2014 | 20-10-2014 | 83 | YES |  |
| 27/21/008/00/G/32907 | 11-11-2014 | Chandrapur | CH/001/14/11018 | 18/11/2014 | 18/11/2014 | 412 | No |  |
| 27/21/008/00/G/33007 | 11-11-2014 | Chandrapur | CH/001/14/11020 | 17-11-2014 | 17-11-2014 | 380 | YES |  |
| 27/21/008/00/G/32708 | 5-11-2014 | Chandrapur | CH/001/14/10881 | 5-11-2014 | 5-11-2014 | 169 | No |  |
| 27/21/008/00/G/34597 | 5-12-2014 | Chandrapur | CH/001/14/12327 | 5-12-2014 | 0 | 0 | 0 | Migrate Droup out On date18-5-2015 |
| 27/21/008/00/G/36340 | 30-12-2014 | Rajura | CH/005/14/5056 | 1/7/2014 | 1/7/2014 | 110 | YES | Death on date13-7-2015 |
| 27/21/008/00/G/36339 | 30-12-2014 | Rajura | CH/005/14/5055 | 30-12-2014 | 30-12-2014 | 650 | YES |  |
| 27/21/008/00/G/35587 | 17-12-2014 | Chandrapur | CH/001/14/13114 | 26-12-2014 | 26-12-2014 | 242 | YES |  |
| 27/21/008/00/G/35586 | 16-12-2014 | Chandrapur | CH/001/14/13072 | 17/12/2014 | 17/12/2014 | 277 | YES |  |
| 27/21/008/00/G/37832 | 14-1-2015 | Rajura | CH/005/15/270 | 14-1-2015 | 14-1-2015 | 498 | No |  |
| 27/21/008/00/G/40200 | 24-3-2015 | Chandrapur | CH/001/15/2897 | 26-3-2015 | 26-3-2015 | 499 | YES |  |
| 27/21/008/00/G/42410 | 13-4-2015 | Warora | CH/002/15/1275 | 15-6-2015 | 15-6-2015 | 356 | YES |  |
| 27/21/008/00/G/44761 | 2-5-2015 | Mul | CH/003/15/1357 | Not Link with ART |  |  |  | Drop OUT |
| 27/21/008/00/G/46402 | 26-6-2015 | Chandrapur | CPR/002/50/08730 | 13-7-2015 | 13-7-2015 | 559 | No |  |
| 27/21/008/00/G/47001 | 4-7-2015 | Rajura | CH/005/15/3090 | 28/7/2015 | 28/7/2015 | 250 | No |  |
| 27/21/008/00/G/50329 | 21-9-2015 | Bhadravati | 3690 | 21-9-2015 | 21-9-2015 | 604 | No |  |
| 27/21/008/00/G/50560 | 15-9-2015 | Bhadravati | CDR/001/10767 | 16-9-2015 | 16-9-2015 | 190 | YES |  |
| 27/21/008/00/G/50726 | 13-9-2015 | Rajura | 3817 | 14-9-2015 | 14-9-2015 | 650 | YES |  |
| 27/21/008/00/G/54157 | 25/11/2015 | Chandrapur | CDR/001/8503 | Not Link To ART |  |  |  |  |
| 27/21/008/00/G/55678 | 15-12-2015 | Warora | 5019 | 15-12-2015 | 15-12-2015 | 116 | YES |  |
| 27/21/008/00/G/55368 | 10-12-2015 | Rajura | CH/005/15/5215 | 15-12-2015 | 15-12-2015 | 760 | No |  |

VII. Financial systems and procedures

Linkages

Systems of planning:

The received fund utilized  equal or below as per the budget approved. All expenditure approved through concern authority.

Systems of payments-

From our verification of books of accounts and other related document we found that, all payments are made through account payee/RTGS method. All supporting documents approved by concern authority also. Found the cash payment below of Rs. 5000/- on the basis urgency.

Systems of  procurement-

Insurance for staff.

AMC computers.

Group Insurance for employees are not done due to unavailability of fund. AMC of Computers also done. As per no need of any procurement process during the April 2015 to March 2016.

Systems of documentation-

A separate Bank account is operated for said project with two signatory

Authority at branch Chandrapur of Union Bank of India. All Bank Reconciliation Statement available. No query at Audit reports. All SOE & UC submitted. Bills and vouchers have been examined and found in order which is subsequently recorded  in tally software version 7.2.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal,  Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

Project manager is qualified and but having partial knowledge about selection of sites,high risk migrants,PL selection etc. and also partiall knowledge about the proposal, Quarterly and monthly plan, financial management, computerization and management of data, knowledge about program performance indicators. Mentoring of field staffs need to more focus and also understand of technical issues of migrants.   A few of the advocacy initiatives were undertaken which could have been in the line of needs of the community as PLs/HRGs.

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

Presently working Counselor is MSW as per NACO norms recently appointed in other project will join on August 2014 Counselor  have  training from MSACS.

Counselor  not having clear knowledge about risk venerability, Clarity on risk assessment and risk reduction types of counseling but clear about  all related formats, knowledge on basic counseling and HIV, symptoms of STIs and syndromic case management , well maintenance and updating of related data and registers.Counselor need to update about counseling technics and types and migrant related indicators.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.

For ANM, adequate abscess management skills.

Not applicable

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc.

Total 10 ORW  presently working  in TI and  The project’s ORWs still need to be versed properly about target on various indicators for their PLs, outreach plan, STI symptoms, RMC and ICTC testing, support to PLs, field level action based on review meetings etc. As per the available records timeliness was followed for submission of their reports. By interviewing respondents at various hotspots, it was reflected that ORWs have got their rapport.

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

VIII f. Peer educators in IDU TI

Prioritization  of  hotspots,  condom  demonstration,  importance  of  RMC  and  ICTC  testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

Not applicable for this TI as evaluated.

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritize the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

1 peers represent the source states (Madhya Pradesh) from where maximum migrants of the area belong to and they are rather able to prioritize the networks/locations where migrants work/reside/access high risk activities. 15 PLs (out of 26) had met during the entire span of the project evaluations. Three female of them were having limited familiarity with the project while twelve was observed rather versed on intervening spots,  ICTC, skills on condom demonstration as well as knowledge  about condom depots, symptoms of STI, issues related to treatment of TB and other project relevant service facilities.

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

Not applicable for this TI as evaluated.

VIII i. M&E officer

Whether the M&E officer (FSW and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

She has a sound knowledge of the project activities and she was able to provide analytical information about the gaps in outreach, service uptake to the project staff. She provided information on various indicators in TI and STI reports. she has all knowledge on all project work.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs.  Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

Not applicable for this TI as evaluated.

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs/PLs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

Through our interactions, all of the ORWs rather understood the number of outreach sessions conducted by ORWs' session plans were shared to PLs to some extent but below 8% were attended..Total 1169  sessions done by ORW PLs 528 attended by ORW. However authentic data were still to be captured by ORWs' for their records.Total 5860 sessions done by PLs 528 attended by ORW.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

Overall service uptake, its quality in the project still need to be as per performance indicators but some of the met migrants as interacted were satisfied by the intervention in terms of message delivery, staffs’ attitude as well as linking towards service uptake.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

The community participation was   visible in context of migrants, married and others which become possible due to mobilizing their direct stakeholders. No doubt, concerns of migrants were captured through meetings but they were not as such involved in planning process. Advocacy efforts were undertaken to some extent but relevant documentations were improper. The benefits of  community’s involvement in monitoring the project activities was yet to be understood by the project team, rather their migrants’ stakeholders- owners/managers had made track on intervention activities who were observed supporting at large.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes.  Method of demand calculation, Female condom programme if any,

The project has 101 number of non-traditional condom outlet which were functional to make the accesses at all the intervening areas. Initially the project made non-traditional outlets Further, in a migrant intervention where condom social marketing (CSM) lead to project sustainability by health seeking behavior of the audience targeted, randomized  marketing/distribution might be avoided through condom depot channels or through PL/ORW and in message delivery systems same could have been incorporated measurably whilst doing BCC by the project team. Female condoms were neither procured nor provisioned through any TI-networks.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

Though the project has not formulated Project Management Committee (PMC) but was able to involve only a few of the potential stakeholders/migrants in some extend in the program activities which is not documented properly. Systematic plan for advocacy was still wanting. However, each of the two ORWs, at their level, doing advocacies and were recorded by themselves. In addition to these advocacy efforts.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

The project had not yet to provide any social protection schemes/ welfare schemes/social entitlements.

XV. Best Practices if any

None of the practices were identified as best ones.