Annexure: B

Reporting Format-B

Structure of the Detailed Reporting  Format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Background of Project and Organisation:

Drushti bahuuddeshiya  Vikas Sanstha registration under society registration Act 1860 and Bombay Public Trust ACT 1950 in the year 2002 the organization is working as NGO. The organization. has its past track of experiences in running following projects :-

| Name of the Project | Funded By | Year | Working Area |
| --- | --- | --- | --- |
| Target Intervention Program | MSACS Mumbai | 2012 | Gondia District |
| Community Service Centre (CSC) | NMP+ Alliance India | 2014 | Gondia District |
| PPTCT | IL & FS Education Technology Service ltd. Delhi | 2007-2015 | Gondia District |
| RNTCP | State TB Control Program, Pune | 2015 | Gondia District |
| Community Care Centre (CCC) | NACO KHPT | 2010-2014 | Gondia District |

- Name and address of the Organization:  Drushti bahuuddeshiya  Vikas Sanstha ,Gondia Maharshtra

- TI-Office Address:  Drushti TI FSW Project near hanuman mandir civil lines,Gondia Maharshtra,441601

- Chief Functionary: Dr. Sachin Choudhary

- Year of establishment: 2002

- Year and month of project initiation: February 2012

- Evaluation team: Sheeba Rahman (Team Leader  & External Evaluator), Ms.Nida Khan (External Consultant),  Bharat  Mohwanshi (Data manager ART center Gondia ,Finance Evaluator)

- Time frame: 26th  April 2016  to  28th April 2016

Profile of TI (Information to be captured)

- Target Population Profile: FSWs

- Type of Project:  :  Core Composite (FSWs )

- Size of Target Group(s): Allocated Target of FSWs- 500, while registered  FSWs-728 population  ,Total-570 active population.

- Sub-Groups and their Size:  FSW-Home-based (HB-477) ,Lodge-(07 ),Dhaba (1)Street based-(45),Highway based (40)

- Target Area: TIs’ hotspots stretched in approx. 100  (Devari) kilometers periphery from the TI office.

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc

The organization has contracted by the MSACS in the month of February 2012 and the appointment

of staff done immediately by the organization.

During de-briefing session, Project Director (PD)-TI  of the NGO were present along with staffs who observed inclined for success of the intervention. The organization’s presence in  Maharastra state was more than a decade and through its various activities and had focused issues associated with HRGs. At an average one monthly meeting was convened during review period and majority of these meetings were attended by PD.

II. Organizational Capacity

Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover:

Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project,

This TI project consists of Project Director (1), Project Manager  (1),  M&E cum account (1), Counselor (1), Out Reach Worker (ORW)-2,Eight  Peer Educators (PEs) are presently participating in the project. The project has no staff turnover  in year 2015-16 Organization  provide staff appointment letters, job description,Some of the leave records were signed by authorized person. Monthly meetings are being organized regularly at the TI office

Organization is supported by MSACS to undertake a TI project and the staffing pattern is as follows:

Following are the staff details:

| Sl No. | Name of the staff+ | Designation | Qualification | Working Since with month |
| --- | --- | --- | --- | --- |
| 1 | Dr.Sacheen N. Choudhary | Project Director-TI | BHMS | 01-08-2012 |
| 2 | Ku. Durgeshwari O. Patle | Project Manager | MSW | 01-11-2014 |
| 3 | Smt. Sandhya G. Shambharkar | Counselor | MSW | 01-10-2015 |
| 4 | Ku. Sangita S. Lanjewar | ORW-1 | MSW | 13-02-2012 |
| 5 | Mr. Sitaram P. Funde | ORW-2 | 12th | 01-04-2013 |
| 6 | Mr. Pravin B. Choudhari | M&E cum Accountant | B.com | 01-04-2014 |

Only one PE turnover is seen in 1 year of span was witnessed through records.  PE-profile is also being given underneath which were working at present.

Outreach Worker-1: Name: Ms Sangeeta Lanjewal

| Sl. No | Name of PE | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Meena Kodape | 36 | 7th | 60(66) | 01.04.2014 | Gondia |
| 2. | Premlata Bhelawe | 31 | 12th | 29(27) | 01.04.2014 | Amgaon |
| 3. | Maheshwari Tekam | 22 | 12th | 66(55) | 01.11.2014 | Tirora |
| 4. | Dileshwari Chute | 25 | 10th | 116(91) | 01.01.2015 | salekasa |

Outreach Worker-2: Name: Mr.Seeta Ram Fhunde

| Sl. No | Name of PE | Age in years | Qualification | Target | Date of Joining | Intervening area |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Ramalabai Sonwane | 58 | 4th | 93(87) | 01.09.2012 | Morgaon Arjuni |
| 2. | Imala Omkar | 49 | 4th | 113(102) | 01.04.2015 | Sadak Arjuni |
| 3. | Payal (Vandana) Patil | 29 | 7th | 87(80) | 01.04.2012 | Goregaon |
| 4. | Lata Shyamkuwar | 40 | 12th | 84(76) | 01.04.2015 | Deori |

Out of 8 PEs 5 were present during the course of evaluation. After done FGD in Chota godia 11 HRGs available they were partially aware about the project services,she all is working under one pimp Ramla bai sonewane who is also PE of the project age of PE is 58 but during discussion she is not know about RMC she said when only symptoms seen I refer to PPP otherwise not and out of 11 only one HRG knew about RMC . Second field visit done in Katangi  5 HRGs available and knew about all services and third visit done in Lakhegaon where  out of 4 ladies all are house wife not HRGs and ORW who is introduce one lady (Shabnam sheikh )as PE but actually she is not PE ,ORW female sites seems doubtful and need HRG validation for home based HRGs..

Over all knowledge of STI services  (Knowledge of RMC)among all HRGs is very partial.

Capacity building training: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

| Sl.No. | Name of staff | Designation | Training given by | Content |
| --- | --- | --- | --- | --- |
| 1 | Durgeshwari Patle | PM | Bopce & Dhanvijay (ICTC) | Outreach management |
| 2 | Sandhya Shambharkar | Counselor | Bopce & Dhanvijay (ICTC) | Outreach management |
| 3 | Sangita Lanjewar | ORW | Bopce & Dhanvijay (ICTC) | Outreach management |
| 4 | Sitaram Funde | ORW | Bopce & Dhanvijay Mam (ICTC) | Outreach management |

In TI  PM, M&E, Counselor & ORWs not received any training by MSACS, It was felt the project staff needs modular trainings for PEs and ORWs should be planned and regular inputs be given to them.

Presently staff capacity is very weak in maximum areas of TI component but specially in symptomatic case management. Symptomatic case management trainings also need to be planned for Counselor,PM and ORWs.

| Sl.No. | Name of staff | Designation | Training given by | Content |
| --- | --- | --- | --- | --- |
| 1 | Durgeshwari Patle | PM | Bopce & Dhanvijay (ICTC) | Outreach management |
| 2 | Sandhya Shambharkar | Counselor | Bopce & Dhanvijay (ICTC) | Outreach management |
| 3 | Sangita Lanjewar | ORW | Bopce & Dhanvijay (ICTC) | Outreach management |
| 4 | Sitaram Funde | ORW | Bopce & Dhanvijay Mam (ICTC) | Outreach management |

Infrastructure of the organization:

The project office is located within  of project near 4 sites and located centralized area. The TI office has necessary furniture, computer, and printer. Both computer and printer are in working condition. DVD and other infrastructure were in TI office, Dogal vdaphone, All TI sites maps are displayed properly along with IEC material. There are one DIC in the TI project. Two Govt.Hospitalls is very near to TI office.

The DIC has display of necessary IEC material; it was found DIC location is very appropriate but HRG footfall is low and minimum utilized by the community; There is 3 room in TI office including one for  Project Manager and M&E cum Accountant and other for ORW including one separate chamber for counselor. There is a working DIC where, pictorial/text condom ,STI  and HIV related IEC etc. Assets’ records were available but not in preprinted register but duly coded.

4.  Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting an feedback mechanism, dissemination and sharing of the reports and documents for technical

inputs if any.

1.Mechanism and adherence to SACS protocols, availability of  documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

The TI is maintaining all the required documents as per SACS protocols; however information is updated and compiled in a systematic way. They are submitting SIMS reports on regular basis.

During the evaluation it was observed that the TI staff was updating data.

All the documents were made available to the evaluation team which shows that it has been maintained as per SACS guidelines. The weekly review meeting and monthly review meetings with the staff were conducted on regular basis Project director attended 12 monthly meetings, Stock registers are maintained but not in preprinted register but duly coded.Although documentation of TI is good but at implementation

III. Program Deliverables

Outreach

Line Listing of HRG by category:

The TI project targeted 500 FSWs however 728 were registered however 552 were registered, Presently 570 FSWs are getting services in the program. HRG having minimum 16   to 58 of age group it also questionable. Line list needed validation for home based HRGs.

Coverage of target population (sub-group wise): Estimated / regular contacts

FSW-Home-based (HB-477) ,Lodge-(07 ),Dhaba (1)Street based-(45),Highway based (40)

The project is working in  Gondia district and has identified 26 sites and 54 hot spots presently for intervention.  The total population being covered by the project is 570, against the target of 500.

As per the SIMS, intervention has been made for 728 registered and 570 active FSWs against the allocated targets of 500. PE Form is used   Over 100% active HRGs reached during last one year and were in 94 % regular contacts during the assessment period.

More than allocated HRG registered with the project and currently more than100% of the allocated target were active as per documents but  as per field implementation it is not as same as documented ,HRG need validation.

Outreach   planning

Outreach planning done but need improvement, ORWs are documanting outreach planning. The plans documented/ prepared by the ORWs need to be implemented on field which was  partially reflected during FGD.

Peer Education

At the time of evaluation there were 08 PEs for 570. The PE: FSWs ratio of 1:60 (1:55,1:91,1:27,1:52,1:76,1:102,1:80,1:87). Based on the distribution of HRGs some PEs has more HRGs ,some is less.

During discussions with PEs, it was observed that their knowledge in context of communication skills for message delivery were found average in terms of project requirements. PEs had their bags where in condoms, IEC were placed, penis model is not available with any of the  PEs

Few of the PEs were relying on ORWs for their planning to achieve various targets within the time frame of the project tenure, e.g. ICTC, referrals/testing etc.PE needs to be capacitate  on STI,RMC & IPC.

Supervision- mechanism, process, follow-up action taken etc.

The TI project has not proper system for monitoring and supervision. Based on the observation and discussion it appears that PD is actively involved in TI project planning and implementation. The PM is visiting the sites and hot spots located close to the TI office. The PM reviews program activities on a monthly basis, but due to untrained staff and partial knowledge  program is badly affected Qualitative GD s were not conducted by ORWs as well as PEs and also home based HRG validation needed immediately.

IV. Services

- Availability of STI services - mode of delivery, adequacy to the needs of the community.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centers.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

- No. of Needles / Syringes distributed through outreach / DIC.

- Information on linkages for ICTC, DOT, ART, STI clinics.

- Referrals and follows up

Availability of STI services:

| Sl. No. | Name of the Doctor | Allopath/non-allopath | Received training on Syndrome Management from SACS/TSU | Letter of Understanding (LOU) signed: Yes/No |
| --- | --- | --- | --- | --- |
| 1. | Dr. Vivek Parate | BAMS | No | Yes |
|  | Dr. Suekha Mankar | BAMS | No | Yes |
|  | Dr. Nafisa Hirkane | BHMS | No | Yes |
|  | Dr. Mohanprasad Tiwari | BHMS | No | Yes |

Meeting with Dr. Vivek Parate  said “I am doing general treatment for cough,cold and fever for all patient not only for HRG” & Dr. Nafisa Hirkane  give brief during discussion that  “80% of general population and 20% of sex workers came to me for treatment”

All 4 PPP are not trained on symptomatic case management PPP doctors referred for drugs for purchase by patient, no drugs and no condoms available with PPPs.

STI services are catered mainly through PPP model four male doctor whose contract was observed signed with the TI on non-judicial bond-paper.

As per discussion with District supervisor and  STI counselors of Govt.hospital Gndia it felt that with out training without internal testing and with of kits PPPs referral is not fruitful it will be more better to refer govt.STI clinic which is very near to TI office sufficient kits was available in hospital.

Linkages (for ICTC/VDRL/ART/TB etc.) as being used by the TI:

- ICTC/VDRL/STI/ART/TB – KTS Hospital, Gondia

- ICTC/ VDRL –BGW Hospital, Gondia

- ICTC-Goregaon,Aam Gaon,Dewari,TIdora,Sadak arjuna,Morgaon arjune,Salekasa(50% testing)

- STI-75%  testing done through PPP .

During ICTC Gondia visit on 27th April  team Ms. Bharti Ghanvijay and Mr. Prakash Bhopchey and Lab technician Mr Hatwar and Lalita B Sharnagat STI Counselor  (Kuanr Tilak Singh Hospital Gondia and  they maintain ICTC testing ,VDRL testing.and also meet ICTC counselor and lab technician of BGW Hospital, Gondia

Availability of STI drugs:

No STI drugs available with TI.

Quality of the services and treatment in the service provisioning:

Infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

The PP Dr. clinic at  Dr. Tiwari,Dr.Nafisa (BHMS),Dr.Surekha Mankar and Dr.Vivek Prate(BAMS)is functional since 2012 and 2015, as the project had adopted PPP model and also govt. referral. four PPP doctor is functional covered all main site of TI.As per record 70% of RMC,STI related treatment done through PPPs but when visiting clinic of  Dr. Vivek Parate he  said I am doing general treatment for cough,cold and fever for all patient not only for HRG and meeting with Dr. Nafisa Hirkane she said we are not aware that we are referred only  for HRGs group she said approx..80% patients are general population. As per all above meetings it is suggested to TSU/SACS that validation of home based HRG needed and symptomatic case management training is essential for all PPP and drug availibility is essential other wise government referral is more better.

Previous 2 years from  April 2014 to March  2016 , over all Rs.63650 amount paid and Rs.213675 booked   for PPPs it was felt that all the above  amount not gives  required result.

Documentation

Availability of treatment registers, referral slips, follow up cards ( as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

The status of documentation, maintain of register was found satisfactory. Line listing, condom stock register, STI drugs stock register ,ICTC referral register, STI treatment register, Asset register, attendance and leave records, staff personal files were maintained. Line listing was updated since April 2012.

Form B merged with form C  is available but filled by ORW, 51% distribution done through free condom in year 2015-16 (81415/202284).However, counseling register and referral register, STD register, STI drug stock register, network clinic form, etc. found maintained and kept at the TI. Treatment Register, referral slips and follow up cards were available.

Availability of Condoms- Type of distribution channel, accessibility, adequacy, No of condoms distributed etc:

Condoms have been procured from MSACS. Condoms are stored at the TI office. Condoms are issued to ORWs who then issue to PEs based on their requirement.  15 outlets have been identified in the project area. These outlets are located at Kirana,Pan shop,dhaba. As per Demand  very low distribution 40% in year 2015 due to stalk out  by the MSACS in (September,October and November,December 2015.)for prolonged period. But CSM done 23080 in year 2015-16.over all 51% demand matched which is very low as per demand .

Condom Details:

| Demand(April 2015 to March 2016) | Free Distribution(April 2015 to March 2016) | CSM |
| --- | --- | --- |
| 202284 | 81415 | 23080 |

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception,     perspectives of these groups towards the project activities.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

FSWs are participating and availing services being rendered by the project.

Two event done in 2015-16,(73 participants attended in two events) event register maintained by TI.

CBO were formed during the current project period. CBO consists of 31 members is active in year 2015-16.

Community participation was rather reflected to significant extent and TI, in last one year, Foot fall in DIC was observed  HRGs monthly is very low approx..  12-15 HRGs. During hotspot-visits some reflection of activities was observed after having interactions in FDGs.

SHG of FSW were made by HRG group in other program.

Details of Committees, if any:

| Name | Designation | Date of establishment | Date of Meetings Conducted (2015-16) |
| --- | --- | --- | --- |
| Program Management Committee | Formed |  |  |
| Crises Management Committee | Dr.Sanjay Agrawal |  | 05.09.2015 |
| DIC Management Committee | Not Formed |  |  |
| Clinical Management Committee | Not Formed |  |  |

VI. Linkages

1.  Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc

2.  Percentages of HRGs tested in ICTC and gap between referred and tested.

3.  Support system developed with various stakeholders and involvement of various stakeholders in the project.

The evaluation team visited ICTC.ICTC staff reported that TI project staff had developed linkages with them. The TI staff accompanied FSWs to the ICTC for HIV &VDRL testing.

Monthly meeting conducted with ICTC.

No FSWs have been referred with Tuberculosis,

| Indicator | 500 |
| --- | --- |
| Total Registration | 728 |
| Drop-out | 158 |
| Active | 570 |
| Condom demand | 202284 |
| Condom distribution | 104495 |
| New registration | 89 |
| ICTC (twice in a year) | 859 |
| Detected positive was found in this year | 3 |
| Link ART | 3 |
| Detected positive cumulative | 31 |
| Link ART | 30 |
| RMC (4 times) | 1961 |
| Syphilis (twice) | 858 |
| Linked to ART |  |
| Total number of individuals counseled by Counselor | 719 |

Detail of Positive HRG:-

| UID | Date of HIV Test | Name of ICTC | PID No | Date of Pre ART registration | Baseline CD 4 test data | Baseline CD 4 Count | Whether put on ART or not | Reason for not getting ART |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 499 | Sep-15 | Deori ICTC | 00315018 | 28/09/2015 | 29/09/2015 | 393 | Yes | ART getting |
| 705 | Jun-15 | Tirora ICTC | GO/003/06/400336 | 27/06/2011 | 27/11/2011 | 396 | Yes | ART getting |
| 720 | Nov-15 | SadakArjuni ICTC | GO/00935/15/480 | 30/11/2015 | 02/12/2015 | 301 | Yes | ART getting |

Financial systems and procedures

- Linkages

- Systems of planning:

As per the Observation of finance we have seen that the monthly planning is done on the basis of approved budget and availability of funds in the respective head. Monthly requirement is fixed calculated in the last week of previous month’s meeting. Cash balance in hand and payment made in cheque.

All expenditure has been booked in the approved accounting head. no change of head has been found during the evaluation. We checked that the SOEs are sent to MSACS monthly on time. Funds for social Marketing have been utilized as budget mention.

- Systems of payments-

Organization has maintained practice for preparation of vouchers. Some of the following observations were found during the verification of the vouchers and relevant documents.

| Sr. No. | Particulars | Status | Remark |
| --- | --- | --- | --- |
| 01 | Machine Number vouchers | Maintained | Yes. Serially maintained |
| 02 | Approval & Authorization | Maintained | Approval taken by PD |
| 03 | Assets Registers | Maintained | Assets registers is maintained and is kept in office. Assets identification no. reflected in the assets. |
| 04 | Bills and Documents | Maintained | Most of the bills found attached with vouchers |
| 05 | Stock Registers | Maintained | Stock register well maintained |
| 06 | Vouchers | Maintained | Pre numbers and pre printed vouchers are kept in separate files, date wise. While checking on random basis it was observe that these vouchers are tallied with cash book and bank statement. |

- Systems of  procurement-

- Insurance for staff..

- AMC computers.

Group Insurance was done. AMC of Computers also done. As per no need of any procurement process during the April 2015 to March 2016.

- Systems of documentation-

Availability of bank accounts (Maintained Jointly, Reconciliation Made on Monthly basis.) The Organization has a bank account in syndicate Bank, being No.51402010005489. The NGO maintained separate bank A/c for their TI project. The bank account is operated by any two amongst two signatory namely president (PD) and vice president. The Organization has done Bank reconciliation on monthly basis. No Query’s found at audit report. SOE and UC submitted. Bills and vouchers have been examined and found in order which is subsequently recorded in tally software version 7.2.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal,  Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

PM’s qualification was as per norm having MSW , joined in 1 november 2014 she  understands and managing program average base. she has partially versed with programme performance indicators.  Review meetings being convened regularly but action taken based on the minutes yet to be incorporated. There was also reflection of her field visits (PM diary , A few of the advocacy initiatives were undertaken which could have been in the line of needs of the community as PEs/HRGs.

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

Counselor  qualification having post-graduate degree in MSW. Joined from 01.10.2014 as a counselor .Counselor not  having  refresher,induction,STI management training from MSACS Counselor knows partial knowledgeabout symptoms of STIs but maintain and updating of all data and registers,Counseling and STI knowledge need to be  strengthen.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction+, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.For ANM, adequate abscess management skills.

Not applicable

VIII d. ORW-1 –Ms. Sangeeta Ganjewal

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc.

ORW qualification is graduate  joined on 13th February 2012  but she is not from HRG group as per ORW interaction.

The project ORW still need to be versed properly about target on various indicators for their PEs, outreach plan, STI symptoms, RMC , support to PEs, field level action based on review meetings etc. ORW still to understand their own roles as expected as per protocol. As per the available records timeliness was followed for submission of MIS.

In outreach plans information were given mainly on condom requirement; analyses on high/medium/low risk; days & time of meeting STI; condom negotiations etc. dues of RMC/ICTC/STI-follow-ups as well as referral and linkages in the access of the community but there was question for authenticity of data. The site-maps were also with some peer educators. By interviewing respondents at various hotspots.

.

ORW-2 Padmavati Naik

ORW qualification having 12th joined on 01 April 2014  as ORW ,male ORW is working for home based population he is still need to be versed properly about target on various indicators for their PEs, outreach plan, STI symptoms, RMC , support to PEs, field level action based on review meetings etc. ORW still to understand their own roles as expected as per protocol. As per the available records timeliness was followed for submission of MIS.

In outreach plans information were given mainly on condom requirement; analyses on high/medium/low risk; days & time of meeting STI; condom negotiations etc. dues of RMC/ICTC/STI-follow-ups as well as referral and linkages in the access of the community but there was question for authenticity of data. The site-maps were also with some peer educators. By interviewing respondents at various hotspots.

.

Peer educators

Out of eight ,five of the peer educators met during evaluations and all five of the PEs knew their project partially some of them were observed having average communication Five PE age is more than 30 years and one PE is running pimp and 58 years of age all PEs capacity building was felt essentially as prime importance. All peers are from the community. Team was able to meet six of them. Peer filled daily diary  on daily basis. No PE were unable to fill- form -B by own  form B and C is merged and filled by ORW  having interactions with respective PEs.

VIII f. Peer educators in IDU TI

Prioritization  of  hotspots,  condom  demonstration,  importance  of  RMC  and  ICTC  testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

Not applicable for this TI as evaluated.

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritize the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

Not applicable for this TI as evaluated.

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

Not applicable for this TI as evaluated.

VIII i. M&E officer

Whether the M&E officer (FSWS+MSMS and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

M&E qualification having B.Com. as per NACO norms  joined  as accountant on 01 April  2014. Fixed asset register maintained but not in preprinted register and proper form, As per the available records timeliness was followed for submission of SIMS. accountant cum M&E officer.

IX. a. Outreach activity in Core TI project

As per the interaction with the team along with peer educators with ORW as well as review of their documents it was apparent that service uptakes were still need to be proper. Evidence based outreach plans still needs to be available wherein frequent visits/monitoring visits could have been properly reflected

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient/appropriate for the truckers/migrants when they can be approached etc.

Not applicable for this TI as evaluated.

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

Service uptake through the project was  visible some of the interacted HRGs screened for ICTC were aware of the services but RMC need to more focus. So far as condom commodity distribution, HRGs observed  partially satisfied .

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

Both ORWs of the staffs was not from the community.

Peer educators as well as a few of the HRGs were included in the list of Crisis Management Committee and SHG  and CBO.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes.  Method of demand calculation, Female Condom Programme if any,

The project level planning for commodity distribution as per As per Demand  very low distribution (104495/202284)51% HRGs were getting free and social marketing condom as per availability which was stocked out (September,October and November,December 2015.)for prolonged period,The distribution channel and tracking system is satisfactory . lubes distribution is very much essential for this area.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

The Stakeholders identification done by TI as per need,need base planning and  advocacies and proper documentation  is in place.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

Social protection scheme

| Sr. No. | Scheme | Achivment |
| --- | --- | --- |
| 1 | Rajiv Gandhi Jivandayi Yojana | 65 |
| 2 | Sanjay Gandhi Niradhar Yojana | 05 |
| 3 | Aadhaar card | 80 |
| 4 | Ration card | 26 |

Best Practices if any

- Formation of SHG

- Formation of CBO (in Process)

- Free Drushti ambulance services

- Regular health camps

- Blood donation camps