Annexure:  B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

- Background of Project and Organisation

Baglan Seva samiti, Nasik is working since 1994 in Nasik and Nadnurbar Districts of the Maharashtra state. The organization is headed by Mr. Raju Shirsath who is Secretary in the organization.

Since last 18 years Baglan Seva samiti is working with various issues such as Health, Water, Education, Natural Resource Management and Sustainable Farming. The Organization is also working in Nandurbar District since 2009 with 10 Gram Panchayats, 63 Padas of Dhadgaon & Akkalkuwa Block of Nandurbar District for overall development. The organization is implementing the various programs like Maharashtra Rural Employment Guaranty Scheme, Community Health Camps, Community Libraries, HIV /AIDS Prevention. Organizations have a Full-fledged regional office in Nandurbar & Nashik city with the all equipments which is needed for the above mention Programs.

Target Intervention Project at Nandurbar District was incepted in 2011 by MSACS under National AIDS Control Programme (NACP). The project was transferred to Baglan Seva samiti from other NGO and earlier it was implemented as Mukta project supported by Pathfinder International. Present TI is Core Composite project covering MSM and TGs of the Akkalkuva, Shahada, Khandbara and Nandurbar blocks of the Nandurbar District in Maharashtra. The organisation has its TI project office at Nandurbar and DIC at Akkalkuva covering 986 HRGs including 26 TGs.

- Name and address of the Organization

Baglan Seva Samiti, CC Project

Near Vivekanand Hospital,

Shakti Sagar Chowk,

Opp. Desai Petrol Pump,

Desaipura Nandurbar – 425412

- Chief Functionary: Mr. Raju Shirsath, Secretary

- Year of establishment : 1994

- Year and month of project initiation : October 2011

- Evaluation team

Mr. Dinesh Prajapati 		– Team Leader

Ms	Purvi Trivedi 			–  Co-Evaluator

Mr. Narendra Sulakshane 	– Finance Evaluator

- Time frame

1st April 14 to 31st March 2016

Profile of TI

(Information to be captured)

- Target Population Profile: TG &  MSM

- Type of Project:  Core Composite Target Intervention Project

- Size of Target Group(s) : Approved – 1000 (TG 100, MSMs 900)

Covered 986 (TG 26, MSMs 960)

- Sub-Groups and their Size

| MSMs | No of HRGs |
| --- | --- |
| Koti | 819 |
| DD | 17 |
| Panthi | 124 |
| TG | 26 |
| Total | 986 |

- Target Area : The TI is implemented in Akkalkuwa, Shahada, Nandurbar and Khandbara areas of Nandurbar District, covering rural and semi urban areas.

Target Areas are from 0.5 KMs to maximum 80 KMs distance covering 10 town areas and 7 Villages.

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

It appeared that the organizational support to the program is very good. However, the secretary and the President of the organization is looking after the project, PD attended only 4 (33%) monthly review meeting in last 12 months. He is well aware with project dynamics and issues of the HRGs. The organization has provided small amount of loans to staff and project in case of delay in fund release from MSACS. Advocacy activities are lead by NGO secretary and have also taken good interest to conduct advocacy at TI level. TI has also taken interest to address community needs and community issues of the community specially for rehabilitation of CLHIV.

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

Currently the TI has a project manager, an Accountant cum M&E, 1 Counselor, 4 ORWs (3 from MSM community), 4 PPP doctors and 17 peer educators to implement the programme. The staff appears committed to the project objectives. There is no staff turnover during the project period and high turnover among peer educators observe. Project Manager is associated with this TI since Oct 2012 and 3 ORWs are working in the TI since Oct – Nov 2011. Attendance register is maintained. Leave registers and file of leave applications is also maintained.

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

In house orientation training was done for the newly recruited staff and peers by the old staff members. Total 5 trainings were conducted at TI level including induction training, training on Social Marketing, Condom, STI management, and TG.

| Sr | Month and Year | Given by STRC/SACS/NGO/TSU/Other | Subject of Training |
| --- | --- | --- | --- |
| 1 | Jul-15 | NGO | Social Marketing Condom |
| 2 | Nov-15 | NGO | HIV, STI, Condom |
| 3 | Dec-15 | Ashiyana Foundation | MSM , TG Program |
| 4 | Dec-15 | NGO | MSM , TG Program |
| 5 | Feb-16 | Pathfinder | MSM |

- Infrastructure of the organization

The organization has a spacious project office cum DIC located at a suitable position that can easily be accessed by the community. The organization is having good infrastructure, which includes, chairs, tables, computers, printer, phone, internet, almirah etc required for the project. There is a television set and DVD kept in the project DIC. All the assets have been codified and marked.

The DIC of both FSW (Separate TI) and CC TI project is same. Similarly Project office is also in same building and on same Floor of same property.

- Documentation and Reporting:

The organization is maintaining all the required documents of the project as per the formats provided by SACS. Dissemination and sharing of the reports for technical inputs was not observed. Documents and records of PE and Counselor needs to be updated on daily basis, and information must be captured for all columns and Rows. The project has been submitting CMIS reports to SACS in time. The field feedbacks are shared and reviewed during weekly staff meetings and monthly review meetings.

It was found that DIC register was updated on monthly and not regular bases at Akkalkuwa site. The Advocacy committee’s meeting minutes were written on the same dates the mentioned ORWs showed their work in the other field and agreed that they didn’t attain the advocacy meeting. Then why it was written in the register? Got no answer.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

Master list of all the 26 TG and 960 MSMs were available in both soft & hard copy form in the project. Each ORW and peers had their own list of HRGs. Completed Registration form of all the HRGs (Form - A) was available. Site map and micro plans based on the line list was available with the PEs.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

Not Applicable for CC TI

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

Not Applicable for CC TI

- Micro planning in place and the same is reflected in Quality and documentation.

There is a site map developed and displayed in the project office. This depicts area wise scenarios and service points. Micro plan was available both for the PEs and the ORWs for delivery of services as per need and demand. Although the ORWs have daily work schedules and plans and the PEs have their own location plans, there is lack of qualitative micro planning & analysis at PE level. All the ORWs and most of the peers have good understanding about the prioritization and risk assessment but still PEs and HRGs have many misconception regarding transmission of HIV/AIDS.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

At present a total of 1118 HRGs were registered by the project and out of which 132 MSMs have been dropped out. 23 new HRGs have been registered in the project period. The current active population is 26 TGs & 960 MSMs. The project has also covered high numbers of PANTHI population and also covered population from villages. It seems that Project is not TI project but mix up of TI and Link Worker project.

- Outreach planning – quality, documentation and reflection in implementation

Outreach plan was prepared and the same was visible in the office. Site map of each ORW is prepared and pasted on the wall. Spot analysis of each site was done by the outreach worker with the help of peers. The documentation of ORWs is maintained properly. Outreach planning is developed and seen in documentation as well as at field level. Tracking of the MSMs for service delivery is also done but needs to be strengthened. PM level documents like Advocacy meeting, Crises Management register, Committee registers etc were not evidence based and quality base.

- PE: HRG ratio :

A total of 17 peers are in place. With little variation in the number of HRGs (1:58 HRGs) with the peers, almost all the PEs is working with the prescribed ratio.

- Regular contacts :

As per the records regular contact is high but the same was not reflecting in the knowledge level of the HRGs. Both the community (MSMs & TG) were aware of their risk and vulnerability but had many misconceptions regarding HIV/AIDS. As per record 92% HRGs contacted twice in a months, but through field interaction it is observed that nearly 70% HRGs are in regular contacts.

During field visit, TI team has failed to make available HRGs at hotspot, and HRGs were gathered at DIC at Nandurbar area. In Akkalkuwa only few HRGs were available for interaction. TI is more than five year’s TI, and ORWs and PM are also working since 5 years but TI intervention is not visible at field.

- Documentation of the peer education

All peers are highly qualified but not a single PE is maintaining form B / Peer diary. Peer diaries are maintained by ORWs. TI is spread in areas of 1 to 80 KMs, so it is question about right and correct data collection when Form B is not maintained by Peers. The risk assessment is done with the help of the peers and maintained by ORWs.

- Quality of peer education- messages, skills and reflection in the community

Total 17 peers are associated with the project. A group discussion was conducted with all the peers. Most of the peers had fair knowledge about routes of transmission and prevention of HIV/AIDS/STIs and about the symptoms of STIs. They had proper understanding about the risk and vulnerability associated with HIV. Some of the Peers were not comfortable to give correct condom demonstration.

- Supervision- mechanism, process, follow-up in action taken etc

PM supervises the project through field visits and through review meeting at TI level. On an average around 11 visits are undertaken by him and documented his observations. The issues pointed out in staff meeting are taken into account.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

TI has developed linkages with 4 BAMS & BUMS Doctors for clinical services, and RMC. Out of 4 doctors appointed, 2 were trained and 2 were not trained on syndromic management guideline. Timings of the clinic are flexible for HRGs. STI drugs are procured from SACS and DAPCU.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

The PPP clinics are located within the project areas and is in close proximity to the hotspots of TOWN areas but very far and away from villages were most of the populations are being covered. It is well equipped. It has an examination table, BP set, surgical tray, and other basic equipment’s. Similarly things required for RMC was also available. Complete privacy is provided to the HRGs visiting clinic as the clinic is established in a separate room.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not Applicable for Core TI

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

Syndromic treatment method is used by the doctor. In the last one year around 41 HRGs has been treated for STI and provided Kit. 16 out of 23 newly registered HRGs were provided with PT. 88% HRGs were undergone for RMC four times in a year. Referal to ART were done and 40 HRGs were detected HIV positive, and all PLHIV identified are linked to ART. A linkage with DOT is also started and 20 PLHIV (50%) and 35 other suspected HRGs were referred to DOT.

1591 HRGs were counseled out of 3723 attended clinic. (43% counseled). In last 12 months, only 35 HRGs were counseled on risk and vulnerability. I.e. 3% only. Not single HRGs were counseled on Risk reduction.

- Documentation-

The counselor is trying to maintain the documents pertaining to clinical services by the project and it was updated. Counselling register is maintained for all the HRGs who have been counselled.  STI drugs stock and condom stock registers are maintained. Referral slips are maintained for all the referrals to ICTC/syphilis screening and DOT centre.

Tracking of HRGs for various types of Counseling and Follow up was not done at TI level. And

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Free condoms are distributed directly through PE/ORWs during one to one or one to group in the community. Good numbers of condom outlets have been identified. Both free and SM condoms were distributed by ORWs, PE, Counselor and outlets. Condom gap analysis were done in each quarter and annual condom demand is around 83,561 and 78440 condoms were distributed.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

78440 pcs of condom were distributed against demand of 83,561 i.e. 93% demand were met through various channel of condom distribution. 12076 pcs of condom were distributed through social marketing which is 15% of total distribution.

- No. of Needles / Syringes distributed through outreach / DIC.

Not Applicable for MSM TI

- Information on linkages for ICTC, DOT, ART, STI clinics.

- Linkages with developed with ICTC of Nandurbar, Khanbara, Akkalkuwa, Molgi, Taloda, Shahada, Khondamali, Dhadgaon, Toranmal, and Mhasawad, for ICTC and VDRL testing.

- 4 Doctors were identified for STI and clinical services.

- For DOT, linkages with DOT centre Nandurbar has been developed, but no referral system developed in areas Akkalkuva, Shahada and Khanbara.

- Linkages with also developed with government department for ADHAR card, Voting card and Social protection schemes.

- Referrals and follows up

Post HIV counseling was done with only 113 HRGs, Follow up of only 51 HRGs were done for ICTC. No data found in counseling register for Post STI Counseling.

TI counselor was not aware about follow up date and CD4 date of PLHIV.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

1 SHG is formed involving 7 members. 1 CBO is formed and registered having 570 MSM HRGs. DIC committee, Project Management committee, Crises committee, and condom committee were formed but not in function. TI has lack of clarity regarding mission, vision and objective of the committees formed and tasks of the committee to be delivered.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

3 MSM HRGs have been promoted as ORWs and participation of HRGs seen as member of the various committees. 1 CBO is formed. Community events were conducted by TI with proper planning and documentation is also available in good manners.

There is need of participation of CBO members in project planning and project implementation.  CBO is struggling for its existence so it is suggested to provide technical support from TSU to CBO for fund raising and income generating activities. Involvement of HRGs in decision making and regulare meeting of the committees is missing at TI level and needs to conduct on regulare interval.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages with 8 ICTCs of Nandurbar districts have been developed for ICTC testing, Additionally, TI has set up PPP ICTC with support of MSACS. Four PPP doctors are identified for STI and RMC, and Doctors are community preferred Doctors and have good faith among community members. Linkages with ART centre, Nandurbar is developed. Additionally linkages with Vihaan are also developed.

However, above efforts have been made for linkages, it is observed that coordination with DAPCU and ICTC is not up to the mark and need to strengthen.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

As TI is implementing PPP ICTC at project office campus, and field testing by PPP ICTC and other ICTCs are permitted, there are no gap between referred and actual visitors at ICTC. 870 (88%) HRGs have undergone for Two times HIV testing at ICTCS.

PPP ICTC is managed by TI staff and as interacted with DAPCU and PPP Doctors, HIV testing done by TI using camp approach at hotspot makes HRGs dependent, and does not motive them to visit ICTC or government facilities. This is become speed breakers for sustainability efforts. It’s also looks that using NGO run PPP ICTC, manipulating in HIV testing is done.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

Linkages with various stake holders are developed and utilized for community development. Adhar cards, voting cards. PAN card, Bank account, Insurance, and benefits of other social protection schemes were provided to HRGs in good manners. Analysis of stake holders and power dynamics needfs to be identified and planned advocacy according to needs of the project must be developed at TI level.

VII. Financial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

Budget guideline is available issued by MSACS Mumbai.  Mostly Expenditure Payment is made as per budget sheet but some expenditures are found over budget.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

  - Used tally software for maintained A/C, separate Printed voucher is available with machine Number. vouchers Number match with tally printed cash or bank books voucher numbers.

  - Stock book available condom and stationary.

  - No pass for payment stamps and sign on bills of  PD. only manually verified by PM (Project Manager) sign on vouchers by secretary, Accountant & Project Manager

  - Supportive document file maintained separately & only bills attached with vouchers

  - Advances taken from staff in cash  for expenses and repayment by cheques But advance register not maintained

  - No Cash transaction found above RS 1000/-and above RS 1000/- payment made by cheque.

- Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

- Quotation were taken from 3 parties, and comparative statement prepared and sign by authority, but seal pockets or Envelope was not available at records..

- Stock register of Condom & stationary was maintained and verified by PM.

- Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

    - Stock & Assets book available

    - Bank Account maintained separately, BRS (Bank reconciliation statement is maintained on monthly basis.

    - Last years Audit Reports are available.

    - F.Y. 2014-2015 Audit compliance report is submitted by NGO to the MSACS

    - Condom Registers maintain properly (like as received from company name, bills no.,

    - Tally Software Printed Cash and bank book was sign by authority.

    - Salary registers, attendance register, leave register (with sanction leave form) was found maintained and updated

    - Cheque issue register available.

VIII. Competency of the project staff

VIII a. Project Manager

The PM is MSW and associated with this project since October 2012. PM has good knowledge and rapport with PEs and HRGs but lacking skill in Program management, team work, and in technical aspects of Target Intervention project.

VIII b. ANM/Counselor

Counselor has done MSW course and joined this TI in July 2014. However, He has conceptual clarity of the project, major indicators of the clinical services and Counseling remain average.. He is engaged in the project since July 2014. He has understanding about the roles and responsibilities of a counselor. He is maintaining and updating all her records according to the guideline.

VIII d. ORW

The project has 4 ORWs; 3 are from community and promoted from PE to ORW. All ORWs are trained by the SACS and NGO level also. The outreach staff has clarity on project activities including project indicators and project documentation and able to perform their role as per NACO guideline. Out of 4 ORWs, 2 are seen most capable for the designation of ORW and rest OTWO are still at learning stage.

VIII e. Peer educators

17 Peer Educators are appointed as per sanctioned. PEs has knowledge and understanding on basics of HIV/STIs and project activities including outreach and services. Most of the PEs is educated but none of them were able to fill Form B. They provide information to ORWs to complete form B. All Peer Educators are trained by TI NGO, and most of them comes under the age group of under 30 years age.

VIII i. M&E officer

Accountant is a Graduate in Commerce (B. Com) and has done certificate in Computer Application and working in this TI since September 2014. Interestingly, He is working as an Accountant only for both the TI and M&E part of the project is seen by other person.

IX. a. Outreach activity in Core TI project

Overall it was observed that outreach activities are satisfactory in the project. It was noticed that DIC attendance is very low and DIC visitor register is maintained on monthly basis and not evidence based. During visit of Akkalkuva DIC, it was observed that board / banner of DIC was not displayed and DIC was without any equipment. Interaction with HRGs shows that only DIC of Nandurbar is utilized in full flagged manner and other two DICs are just a place to reach target of number of DICs.

The documents for outreach are maintained at project level however the analysis of the data to have important conclusions that help in the intervention process needs improvement. Moreover the hotspot wise micro plan, condom & Lube demand & gap analysis, individual tracking for service delivery is done in the project. Outreach activities were undertaken on regular basis. The capacity of the peers need to be strengthened and focused one to one required in the field. Lot of myths and misconception prevailed. Clear messages on basics of HIV/AIDS/STI needs to be disseminated especially among FSWs.

TI has covered 124 PANTHI MSM and during meeting with Peer Educators, it was come out that each PE has 15 to 20 PANTHIS which are registered (TI has 17 PEs so estimated 250 to 300 PANTHIs registered). It is strongly suggested to drop out PANTHI MSM and MSM who are less or not active and are old aged.

X. Services

Most of the service uptake is satisfactory in the project however; the counselor needs to prioritize her work. PLHIV need to be follow up for CD4 test and proper counseling. All newly registered HRGs needs to cover in DIC / Hotspot meeting and also needs to provide PT immediate after registration.

XI. Community involvement

CBO and SHG formation has been done. CBO is active and TI needs to involve CBO is planning and delivering TI services and activities. Since the project is more than five years old the organization may think beyond just implementing TI and its activities.

XII. Commodities

Free condoms are provided to the HRGs by the peers, Apart from this STI drugs are also provided to the HRGs. Apart from this there is need of Lubes among MSM HRGs and TI is in process to procure lubes but not provided till date of evaluation.

XIII. Enabling environment

Advocacy meetings were carried out on need based without proper planning and follow action is lacking after advocacy. ORWs who shown as present in advocacy meetings were somewhere else in field on that time. A crisis management team has been formed but no major crisis reported from the field. In Akkalkua DIC, There was no board found outside the DIC. There was no record of DIC events or regular visits by the KPs.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, 	social entitlements etc.

As reported by Project team, HRGs were provided skill based training to with objective to make them economically sustained. Additionally TI has provided benefit of following schemes.

| Ration Card | Adhar Card | Election Card | PAN Card | Bank A/C | Jandhan Yojana | Insurance | Sanjay Gandi Yojana | Gharkul Yojana | Antyodaya Anna Yojana scheme |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 761 | 849 | 799 | 113 | 439 | 57 | 20 | 5 | 53 | 30 |

XV. Best Practices if any

TI has provided benefit of numbers of schemes. TI has tried to rehabilitate children affected by HIV, There is need of process documentation for this types of activities / works.

Annexure C

Confidential                                                 Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Dinesh Prajapati | 721-722, Kanan Society, Rajan Nagar, Valsad Pardi Road, Abrama, Valsad – 396145, Gujarat – India M : +91 9408333476 Email: dinesh_bsw@yahoo.com |
| Ms. Purvi Trivedi | 52-‘SUJATA’, Vastu Park Society, Jachak nagar, Jai Bhavani Road, Nashik Road, Nashik- 422101, Maharashtra M : +91 9420694488 |
| Mr. Narendra Sulakshane | M : +91 7588686492 E mail : sulakshanend@gmail.com |
| Officials from SACS/TSU (as facilitator) | Mr. Nitin Mandlik DPO, DAPCU, Nandurbar M : +91982234863 |

| Name of the NGO: | Baglan Seva Samiti |
| --- | --- |
| Typology of the target population: | Core Composite (TG & MSMS) |
| Total population being covered against target: | 986 covered against target of 1000 |
| Dates of Visit: | 17/04/2016 to 18/04/2016 |
| Place of Visit: | Nandurbar, Akkalkuva, Shahada, Khanbara, Navapur, Dist : Nandurbar (Maharashtra) |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| 61%-80% (63.7%) | B | Good | Recommended for continuation with specific recommendation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- Organisation failed to secure minimum 79% marks in ORganisation capacity and could get only 71% but considering its transparent finance system and program outreach, Evaluation team recommended this TI for continuation with specific recommendation. - TI has covered 124 PANTHI MSM and during meeting with Peer Educators, it was come out that each PE has 15 to 20 PANTHIS which are registered (TI has 17 PEs so estimated 250 to 300 PANTHIs registered). It is strongly suggested to drop out PANTHI MSM and MSM who are less or not active and are old aged. - TI has failed to cover TG population as only 26 HRGs were covered against target of 100 and that too not in regular contacts, After drop out of PANTHI’s and TG, Data validation of HRGs must be done in strict supervision of DAPCU and TSU and only vulnerable HRGs needs to be covered now onwards. - PPP ICTC is managed by TI staff, and as interacted with DAPCU and PPP Doctors, HIV testing done by TI using camp approach at hotspot, this makes HRGs dependent, and does not motive them to visit / use ICTC or government facilities. This also becomes speed breakers for sustainability efforts. It’s also looks that using NGO run PPP ICTC, manipulating in HIV testing is done. So it is strongly recommended to discontinue / stop PPP ICTC attached with this NGO/TI, and efforts shall be made to provide HIV testing services using ICTC available at government structure. - The capacity of the peers need to be strengthened and focused one to one required in the field. Lot of myths and misconception prevailed. Clear messages on basics of HIV/AIDS/STI needs to be disseminated especially among FSWs. - PLHIV registered with Project needs to be followed up for regular CD4 test and counseling. - Ensure the participation of the newly registered HRGs in the Hotspot/DIC meetings, so as to make them more comfortable with the project services. - Though the uptake of the clinical services is satisfactory, counseling of each and every HRG need focus. Number of HRGs counseled every month is less. Follow up STI patient must be ensured. Pre STI, Post STI, Risk Assessment and Risk reduction counseling shall be provided to HRGs. - Coordination with DAPCU and ICTCs needs to strengthen. It is observed that TI has understating that DAPCU is outside agency, but as per guideline DAPCU is District level unit of MSACS, and TI needs to follow instructions, inputs and feedback of the DAPCU for implementation of TI. - Doctor who are BAMS and BUMS and are untrained are shall be provided training on syndromic management. - During field visit, TI team has failed to make available HRGs at hotspot, and HRGs were gathered at DIC at Nandurbar area. In Akkalkuwa only few HRGs were available for interaction. TI is more than five year’s TI, and ORWs and PM are also working since 5 years but TI intervention is not visible at field. It makes questions on TI’s claim about 98% regular contacts. Efforts shall be made to increase field visibility. - There is need of participation of CBO members in project planning and project implementation. CBO is struggling for its existence so it is suggested to provide technical support from TSU to CBO for fund raising and income generating activities.

Name of the evaluators				Signature

| Mr. Dinesh Prajapati (Team Leader) |  |
| --- | --- |
| Ms. Purvi Trivedi (Co-Evaluator) |  |
| Mr. Narendra Sulakshane (Finance Evaluator) |  |