Annexure:  B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

- Background of Project and Organization

Baglan Seva samiti, Nasik is working since 1994 in Nasik and Nadnurbar Districts of the Maharashtra state. The organization is headed by Mr. Raju Shirsath who is Secretary in the organization.

Since last 18 years Baglan Seva samiti is working with various issues such as Health, Water, Education, Natural Resource Management and Sustainable Farming. The Organization is also working in Nandurbar District since 2009 with 10 Gram Panchayats, 63 Padas of Dhadgaon & Akkalkuwa Block of Nandurbar District for overall development. The organization is implementing the various programs like Maharashtra Rural Employment Guaranty Scheme, Community Health Camps, Community Libraries, HIV /AIDS Prevention, etc. for overall development. Organizations have a Full-fledged regional office in Nandurbar & Nasik city with the all equipments which is needed for the above mention Programs.

Target Intervention Project at Nandurbar District was incepted in October 2011 by MSACS under National AIDS Control Programme (NACP). Present TI is Core TI project on FSWs of the Akkalkuva, Shahada, Khandbara and Nandurbar blocks of the Nandurbar District in Maharashtra. The organization has its TI project office at Nandurbar and DIC at Akkalkuva covering 1098 FSWs HRGs.

- Name and address of the Organization

Baglan Seva Samiti, FSW TI

Near Vivekanand Hospital,

Shakti Sagar Chowk,

Opp. Desai Petrol Pump,

Desaipura Nandurbar – 425412

- Chief Functionary: Mr. Raju Shirsath, Secretary

- Year of establishment : 1994

- Year and month of project initiation : October 2011

- Evaluation team

Mr. Dinesh Prajapati 		– Team Leader

Ms	Purvi Trivedi 			–  Co-Evaluator

Mr. Narendra Sulakshane 	– Finance Evaluator

- Time frame

1st April 14 to 31st March 2016

Profile of TI

(Information to be captured)

- Target Population Profile: FSWs

- Type of Project:  Core Target Intervention Project on FSWs

- Size of Target Group(s) : Approved – 1100 FSWs

Covered 1098 FSWs

- Sub-Groups and their Size

| Brothel | 348 |
| --- | --- |
| Home Based | 742 |
| Lodge Based | 8 |
| Total | 1098 |

- Target Area : The TI is implemented in Akkalkuwa, Shahada, Nandurbar and Khandbara areas of Nandurbar District, covering rural and semi urban areas. TI is covering target areas.

Target Areas are from 0.5 KMs to maximum 58 KMs distance.

| Sr. No. | Name of Target area | No Of Hotspot | Village / City | Distance from Project Office | Home Based | Brothel Based | Lodge Based | No. of HRG |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Nandurbar | Bagawan Galli | City | 0.5 Km | 4 | 0 | 0 | 4 |
| 2 | Nandurbar | Bhoi Galli | City | 0.5 Km | 3 | 0 | 0 | 3 |
| 3 | Nandurbar | Dhud Dairy | City | 1 Km | 0 | 75 | 0 | 75 |
| 4 | Nandurbar | Ekata Nagar | City | 2 Km | 7 | 0 | 0 | 7 |
| 5 | Nandurbar | Gavali wada | City | 0.5 Km | 3 | 0 | 0 | 3 |
| 6 | Nandurbar | Kali Masjid | City | 1 Km | 20 | 0 | 0 | 20 |
| 7 | Nandurbar | Maniyar Mohhala | City | 1 Km | 13 | 0 | 0 | 13 |
| 8 | Nandurbar | Mirchi Gali | City | 0.5 Km | 0 | 54 | 0 | 54 |
| 9 | Nandurbar | Sangam Tekadi | City | 1 Km | 0 | 65 | 0 | 65 |
| 10 | Nandurbar | Sakrinaka | City | 1 Km | 19 | 0 | 0 | 19 |
| 11 | Nandurbar | Tokartalav | village | 6 Km | 3 | 0 | 0 | 3 |
| 12 | Khandbara | Bhadaval | Village | 27 Km | 9 | 0 | 0 | 9 |
| 13 | Khandbara | Chimanipada | Village | 29 Km | 4 | 0 | 0 | 4 |
| 14 | Khandbara | Dewalaphali | Village | 27 Km | 78 | 0 | 0 | 78 |
| 15 | Khandbara | Dogegaon | Village | 26 Km | 6 | 0 | 0 | 6 |
| 16 | Khandbara | Kasare | Village | 29 Km | 3 | 0 | 0 | 3 |
| 17 | Khandbara | Khandbara | city | 25 Km | 133 | 0 | 0 | 133 |
| 18 | Khandbara | Kherava | Village | 28 Km | 5 | 0 | 0 | 5 |
| 19 | Khandbara | Nawapada | Village | 27 Km | 17 | 0 | 0 | 17 |
| 20 | Khandbara | Nijampur | Village | 27 Km | 7 | 0 | 0 | 7 |
| 21 | Khandbara | Pimapla | Village | 29 Km | 7 | 0 | 0 | 7 |
| 22 | Khandbara | Shrawani | Village | 28 Km | 9 | 0 | 0 | 9 |
| 23 | Khandbara | Vatavi | Village | 24 Km | 7 | 0 | 0 | 7 |
| 24 | Akkalkuwa | Bazar Chouk | City | 48 Km | 38 | 0 | 0 | 38 |
| 25 | Shahda | Dongargaon | Village | 42 Km | 60 | 0 | 0 | 60 |
| 26 | Shahda | Lonkheda | Village | 43 Km | 75 | 0 | 0 | 75 |
| 27 | Shahda | Bajarang Colony | City | 42 Km | 6 | 0 | 0 | 6 |
| 28 | Shahda | Sutgirani | Village | 45 Km | 22 | 0 | 0 | 22 |
| 29 | Shahda | Yogeshwar Colony | Village | 41 Km | 3 | 0 | 0 | 3 |
| 30 | Shahda | Garib Navaj Colony | City | 41 Km | 17 | 0 | 0 | 17 |
| 31 | Shahda | Indira Market | City | 40 Km | 0 | 154 | 0 | 154 |
| 32 | Shahda | Saldar Nagar | City | 41 Km | 39 | 0 | 9 | 48 |
| 33 | Shahda | Shahada | City | 39 Km | 98 | 0 | 0 | 98 |
| 34 | Shahda | Prabhudatta Nagar | Village | 41 Km | 27 | 0 | 0 | 26 |
|  |  |  |  |  | 742 | 348 | 9 | 1098 |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

It appeared that the organizational support to the program is very good. However, the secretary and the President of the organization is looking after the project, PD attended only 5 (41%) monthly review meeting in last 12 months. He is well aware with project dynamics and issues of the HRGs. The organization has provided small amount of loans to staff and project in case of delay in fund release from MSACS. Advocacy activities are lead by NGO secretary and have also taken good interest to conduct advocacy at TI level. TI has also taken interest to address community needs and community issues of the community specially for rehabilitation of CLHIV.

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

Currently the TI has a project manager, an Accountant cum M&E, 1 Counselor, 4 ORWs, 4 PPP doctors and 18 peer educators to implement the programme. The staff appears committed to the project objectives. There is limited staff turnover during the project period and high turnover among peer educators observe. Project Manager is associated with this TI since Oct 2012 and 3 ORWs are working in the TI since Oct – Nov 2011. Attendance register is maintained. Leave registers and file of leave applications is also maintained.

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

In house orientation training was done for the newly recruited staff and peers by the old staff members. Total 5 trainings were conducted at TI level including induction training, training on Social Marketing, Condom, STI management etc

- Infrastructure of the organization

The organization has a spacious project office cum DIC located at a suitable position that can easily be accessed by the community. The organization is having good infrastructure, which includes, chairs, tables, computers, printer, phone, internet, almirah etc required for the project. There is a television set and DVD kept in the project DIC. All the assets have been codified and marked.

The DIC of both FSW (Separate TI) and CC TI project is same. Similarly Project office is also in same building and on same Floor of same property.

- Documentation and Reporting:

The organization is maintaining all the required documents of the project as per the formats provided by SACS. Dissemination and sharing of the reports for technical inputs was not observed. Documents and records of PE and Counselor needs to be updated on daily basis, and information must be captured for all columns and Rows.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

Line listing of all 1098 active population was done. Completed Registration form of all the HRGs (Form - A) was available.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

Not Applicable for CC TI

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

Not Applicable for CC TI

- Micro planning in place and the same is reflected in Quality and documentation.

There is a site map developed and displayed in the project office. This depicts area wise scenarios and service points. Micro plan was available with ORWs only and PEs are not able to fill Form B nor able to do prioritization of HRGs base on risk and vulnerability, there is lack of qualitative micro planning & analysis at PE level.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

At present a total of 1679 HRGs were registered and 581 were dropped out and 1098 was active population. 39 new HRGs have been registered in the project period.

  - The project has also covered high numbers of Home based population and population from villages which are 1 to 48 KM’s distance.

  - The TI project is also covering some long distance which is 20 to 48 KM’s distance and having 4 to 10 HRGs.

  - It seems that Project is not TI project but mix up of TI and Link Worker project.

- Outreach planning – quality, documentation and reflection in implementation

Outreach plan was prepared and the same was visible in the office. Site map of each ORW is prepared and pasted on the wall. Spot analysis of each site was done by the outreach worker with the help of peers. The documentation of ORWs is maintained properly. Outreach planning is developed and seen in documentation as well as at field level.

It is observed that PM is not visiting target areas regularly. Only Akkalkuva site which have only 38 FSW HRGs are found visited again and again as it is home town of lady PM. It was observed that areas like Khanbara were not visited by PM and during evaluation visit, she came 1st time in this area. It was also noted that lady PPP Doctor of Shahada (from where 509 HRGs are taking clinical services) was not familiar with lady PM of TI, and Doctor asked for PM’s introduction.

- PE: HRG ratio :

A total of 18 peers are in place. 1:58 HRGs ratio observed.

- Regular contacts :

As per the records regular contact is high as 94% but the same was not reflecting during site visits during evaluation. PEs and ORWs denied for interaction with Home based sex workers (which are 742 FSWs as per line listing). Evaluation team comprises One Female Evaluator, but not a single home based FSW was made available to interact about project services. 10 year old PEs and 5 to 8 year old HRGs were denied to talk on condoms, which raise question that whether claimed home based FSWs are FSWs or NOT. It also shows that when TI has 94% regular contact and providing project related services to HRGs twice in a month then why HRGs were not available for interaction and FGDs.

Secondly, TI has good rapport with brothel based FSWs and ORW’s committed work seen in brothel based FSWs, to which evaluation team appreciate.

- Documentation of the peer education

All peers are educated but not a single PE is maintaining form B / Peer diary. Peer diaries are maintained by ORWs. TI is spread in areas of 1 to 48 KMs, so it is question about right and correct data collection when Form B is not maintained by Peers.

- Quality of peer education- messages, skills and reflection in the community

A group discussion was conducted with all the peers. Most of the peers had fair knowledge about routes of transmission and prevention of HIV/AIDS/STIs and about the symptoms of STIs. Some senior Peers are not in control of ORWs and PM also, which affect project achievement. Additionally, TI has some old age PEs which needs to replace slowly.

- Supervision- mechanism, process, follow-up in action taken etc

PM visits to field areas found very low and PM’s visits were up to Nandurbar (Where TI has project office) and Akkalkuwa (which is her home town) only. Areas like Shahada, and Khandbara were neglected for supervision and monitoring. PM has conducted weekly PE meeting and monthly review meeting with all staff  and PEs are also conducted.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

TI has developed linkages with 4 BAMS & BUMS Doctors for clinical services, and RMC. Out of 4 doctors appointed, 2 were trained and 2 were not trained on syndromic management guideline. Timings of the clinic are flexible for HRGs. STI drugs are procured from SACS and DAPCU.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

The PPP clinics are located within the project areas and is in close proximity to the hotspots of TOWN areas but very far and away from villages were most of the populations are being covered.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not Applicable for Core TI

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centers.

Doctors have good rapport with HRGs and are familiar with issues, dynamics and problems of the community. Doctors appointed and interacted at Shahada and Nandurbar are actively involved in project activities. As inferred from interaction, Doctors are following syndromic Management guideline and providing drugs in from of KIT.

- Documentation-

Documentation at ORW and PM level is up to the mark and as per SACS protocol. Documentation at PE level found weak and PE do not maintained form B at their level. Tracking of HRGs for various types of Counseling and Follow up was not done at TI level. And

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Both Free and SM condom were distributed through PE, ORWs and Outlets. 410360 were yearly condom demand, and 260034 condoms were distributed. 63% demand was met against requirement. 43868 condoms were distributed through SM, 216166 were free condom distribution. Total distribution was 260034 condoms.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

Regular contact is 96% and condom distribution was 63%, so its question about quality of services provided during the One to One contact.

- No. of Needles / Syringes distributed through outreach / DIC.

Not Applicable for MSM TI

- Information on linkages for ICTC, DOT, ART, STI clinics.

- Linkages with developed with ICTC of Nandurbar, Khanbara, Akkalkuwa, Molgi, Taloda, Shahada, Khondamali, Dhadgaon, Toranmal, and Mhasawad, for ICTC and VDRL testing.

- 4 Doctors were identified for STI and clinical services.

- For DOT, linkages with DOT centre Nandurbar has been developed, but no referral system developed in areas Akkalkuva, Shahada and Khanbara.

- Linkages with also developed with government department for ADHAR card, Voting card and Social protection schemes.

- Referrals and follows up

TI has not done follow up of PLHIV.  Only 161 (out of 1098) HRGs were counseled for Pre HIV test.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

CBO is formed and registered having 1077 FSW HRGs.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

DIC committee, Project Management committee, Crises committee, and condom committee were formed but not in function. TI  has lack of clarity regarding mission, vision and objective of the committees formed and tasks of the committee to be delivered.

There is need of participation of CBO members in project planning and project implementation.  CBO is struggling for its existence so it is suggested to provide technical support from TSU to CBO for fund raising and income generating activities. Involvement of HRGs in decision making and regular meeting of the committees is missing at TI level and needs to conduct on regular interval.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages with 8 ICTCs of Nandurbar districts have been developed for ICTC testing, Additionally, TI has set up PPP ICTC with support of MSACS. Four PPP doctors are identified for STI and RMC, and Doctors are community preferred Doctors and have good faith among community members. Linkages with ART centre, Nandurbar is developed, Additionally linkages with Vihaan are also developed.

However, Above efforts have been made for linkages, it is observed that coordination with DAPCU and ICTC is not up to the mark and need to strengthen.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

As TI is implementing PPP ICTC at project office campus, and field testing by PPP ICTC and other ICTCs are permitted, there are no gap between referred and actual visitors at ICTC. 870 (88%) HRGs have undergone for Two times HIV testing at ICTCS.

PPP ICTC is managed by TI staff and as interacted with DAPCU and PPP Doctors, HIV testing done by TI using camp approach at hotspot makes HRGs dependent, and does not motive them to visit ICTC or government facilities. This is become speed breakers for sustainability efforts. It’s also looks that using NGO run PPP ICTC, manipulating in HIV testing is done.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

It was inferred from records that TI has good rapport with Stake holders, but TI team failed to make available stake holders for interaction during evaluation.

VII. Financial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

Budget guideline is available issued by MSACS Mumbai.  Mostly Expenditure Payment is made as per budget sheet but some expenditures are found over budget.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

  - Used tally software for maintained A/C, separate Printed voucher is available with machine Number. vouchers Number match with tally printed cash or bank books voucher numbers.

  - Stock book available condom and stationary.

  - No pass for payment stamps and sign on bills of  PD. only manually verified by PM (Project Manager) sign on vouchers by secretary, Accountant & Project Manager

  - Supportive document file maintained separately & only bills attached with vouchers

  - Advances taken from staff in cash  for expenses and repayment by cheques But advance register not maintained

  - No Cash transaction found above RS 1000/-and above RS 1000/- payment made by cheque.

- Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

- Quotation were taken from 3 parties, and comparative statement prepared and sign by authority, but seal pockets or Envelope was not available at records..

- Stock register of Condom & stationary was maintained and verified by PM.

- Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

    - Stock & Assets book available

    - Bank Account maintained separately, BRS (Bank reconciliation statement is maintained on monthly basis.

    - Last years Audit Reports are available.

    - F.Y. 2014-2015 Audit compliance report is submitted by NGO to the MSACS

    - Condom Registers maintain properly (like as received from company name, bills no.,

    - Tally Software Printed Cash and bank book was sign by authority.

    - Salary registers, attendance register, leave register (with sanction leave form) was found maintained and updated

    - Cheque issue register available.

VIII. Competency of the project staff

VIII a. Project Manager

Pushplata Chetram Bramhane is Project Manager at TI and she has done MSW, also having 5 years experienceof working with TI project. She joined this TI in October 2012. PM has good knowledge about HIV/AIDS and TI project, but due to her limited field visit she does not have grip on field intervention. During field visit, it was observed that she is visiting some areas (Shahada, Khanbara sites) first time (She is working with this TI since last 4 years). She was not able to manage some old peer educators and her command was up to records and office only. Its is observed that she has done field visit mostly in Akkalkuva as he is her residential place, from where few HRGs are in regular contact.

VIII b. ANM/Counselor

Bipin Prabhakar Patil is Counselor. He has done his Master in Psychology and joined this TI in October 2011. He has conceptual clarity of the project but failed to provide all 7 types counseling services to HRGs and mostly focused on HIV testing.

VIII d. ORW

The project has 4 ORWs; 2 have completed their Master degree, One is graduated and one is 10th passed. The outreach staff has clarity on project activities including projean five years old TI, and many peer educators are working since inception of the project, TI needs to promote community members as ORW.

VIII e. Peer educators

PEs has knowledge and understanding on basics of HIV/STIs and project activities including outreach and services. Most of the PEs is less educated so none of them was able to fill Form B. They provide information to ORWs to complete form B. Most of them are old and abovce 30 years. Some PEs are more than 50 years age.

VIII i. M&E officer

M&E officer cum Accountant is a Graduate in Psychology and not qualified for the post of M&E officer. He is working with this TI since April 2012. However, he is not qualified but by work experience he is able to perform all M&E related tasks effectively.

IX. a. Outreach activity in Core TI project

Out Reach activities found as an AVERAGE at FSW TI level.

X. Services

Most of the service uptake is satisfactory in the project however; the counseling part is weak and TI needs to focus on all 7 types of the counseling services. Specially, risk reduction and risk assessment counseling of each HRGs must be done once in a year. Same follow up of PLHIV and planning of their CD4 test shall be done as per schedule. All newly registered HRGs needs to cover in DIC / Hotspot meeting and also needs to provide PT immediate after registration.

XI. Community involvement

CBO and SHG formation has been done. CBO is active and TI needs to involve CBO is planning and delivering TI services and activities. Since the project is more than five years old the organization may think beyond just implementing TI and its activities.

XII. Commodities

Free condoms, Free STI drugs and SM condoms were provided to HRGs.

XIII. Enabling environment

13 Advocacy meetings were carried out covering all important stake holders with proper documentation and follow up actions. 4 events were conducted and 259 HRGs were participated (24%).

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, 	social entitlements etc.

As reported by Project team, HRGs were provided skill based training, Ration card, Voting card, PAN card, Bank account facility etc.

XV. Best Practices if any

TI has provided benefit of numbers of schemes. TI has tried to rehabilitate children affected by HIV, There is need of process documentation for this types of activities / works.

Annexure C

Confidential                                                 Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Dinesh Prajapati | 721-722, Kanan Society, Rajan Nagar, Valsad Pardi Road, Abrama, Valsad – 396145, Gujarat – India M : +91 9408333476 Email: dinesh_bsw@yahoo.com |
| Ms. Purvi Trivedi | 52-‘SUJATA’, Vastu Park Society, Jachak nagar, Jai Bhavani Road, Nasik Road, Nasik- 422101, Maharashtra M : +91 9420694488 |
| Mr. Narendra Sulakshane | M : +91 7588686492 E mail : sulakshanend@gmail.com |
| Officials from SACS/TSU (as facilitator) | Mr. Nitin Mandlik DPO, DAPCU, Nandurbar M : +91982234863 |

| Name of the NGO: | Baglan Seva Samiti |
| --- | --- |
| Typology of the target population: | Core FSWs |
| Total population being covered against target: | 1098 covered against target of 1100 |
| Dates of Visit: | 19/04/2016 to 20/04/2016 |
| Place of Visit: | Nandurbar, Akkalkuva, Shahada, Khanbara, Navapur, Dist : Nandurbar (Maharashtra) |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| 61%-80% (61.2%) | B | Good | Recommended for continuation with MERGER IN CC TI. |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

- Specific Recommendations:

- Organization failed to secure minimum 79% marks in Organization capacity and could get only 71%. - PPP ICTC is managed by TI staff, and as interacted with DAPCU and PPP Doctors, HIV testing done by TI using camp approach at hotspot makes HRGs dependent, and does not motive them to visit / use ICTC or government facilities. This is become speed breakers for sustainability efforts. It’s also looks that using NGO run PPP ICTC, manipulating in HIV testing is done. So it is strongly recommended to discontinue / stop PPP ICTC attached with this NGO/TI, and efforts shall be made to provide HIV testing services using ICTC available at government structure. - Though the uptake of the clinical services is satisfactory, counseling of each and every HRG need focus. Number of HRGs counseled every month is less. Follow up STI patient must be ensured. Pre STI, Post STI, Risk Assessment and Risk reduction counseling shall be provided to HRGs. - Coordination with DAPCU and ICTCs needs to strengthen. It is observed that TI has understating that DAPCU is outside agency, but as per guideline DAPCU is District level unit of MSACS, and TI needs to follow instructions, inputs and feedback of the DAPCU for implementation of TI. - Doctor who are BAMS and BUMS and are untrained are shall be provided training on syndromic management. - PMs visit for all hotspots according to need of the project shall be ensured. - Condom demand shall be reached through proper planning and provision of more brands of Socially marketed brands of condoms. - Documentation of Peers needs to be strengthening. - TI has covered 742 home based FSWs and many of them are from rural villages. Evaluation team observed that this population is not Vulnerable RISK of HIV population. It is suggested to do revalidation of HRGs under direct supervision of DAPCU and TSU and only Vulnerable HRGs are to be covered from next project year. - Same TI has covered villages based population having 3 to 19 HRGs, As TI is working on LWS project guideline and this population which is in smaller amount (and home based), and 20 to 48 KM’s distance needs to be drop out. - Following Similarities were observed by Evaluation team in TWO TI implemented by Baglan Seva Samiti in Nandurbar : - TI has same project office for both project (3 Rooms building) for which rent from both project was claimed. - Both TI has same DIC (which is attached to TI office but rent is claimed separately). - Thus, for FOUR room building, rent from 3 budget head was claimed and booked). - Both TI has same DIC for FSWs and MSMs in Akkalkuva. - Both TI has same PPP Doctors. - Target areas of both TIs are same. - ICTC, ART and other referral centers are same for both TIs. - Same person is maintaining Account of both TIs. - Same person is working as M&EA for both TIs. - Same person is Project Director for both TIs. - MSM TI has large number of PANTHI population (which shall be not register as per guideline. - FSW TI has large number of home based, Rural and non Vulnerable population. - TI has failed to reach TG population in CC TI and not willing to cover TG population. - Considering above points, noticing field observations, keeping in mind feedbacks of DAPCU, PPP Doctors, and TSUs; Evaluation team strongly recommend to Merge FSW and CC TI in ONE CC TI of FSWs and MSMs (leaving TG) instead of TWO separate TI. (After Drop out of PANTHIs and Non Vulnerable Home based FSWs TI size will be fit for one unit / project)

Name of the evaluators				Signature

| Mr. Dinesh Prajapati (Team Leader) |  |
| --- | --- |
| Ms. Purvi Trivedi (Co-Evaluator) |  |
| Mr. Narendra Sulakshane (Finance Evaluator) |  |