Annexure C

Reporting form C

Confidential

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

|  |  |
| --- | --- |
| Name of the evaluators | Contact Details with phone no. |
| Mathivanan R | [ira.mathivanan@gmail.com](mailto:ira.mathivanan@gmail.com) , mob: 09840231989 |
| Purvi Trivedi | phtrivedius@yahoo.com, Mob: 09420694488 |
| Shailesh Patil | **+91 7028381187** |
| Officials from SACS/TSU (as facilitator) |  |

|  |  |
| --- | --- |
| Name of the NGO: | Magmo Welfare Sanstha |
| Typology of the target population: | Migrants |
| Total population being covered against target: | 18615 against 15000 migrants |
| Dates of Visit: | 27th and 28th April 2016 |
| Place of Visit: | Nashik |

Overall Rating based programme delivery score:

|  |  |  |  |
| --- | --- | --- | --- |
| Total Score Obtained (in %) | Category | Rating | Recommendations |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| ***61%-80%*** | ***B*** | ***Good*** | ***Recommended for continuation*** |
| **89.7%** | **A** | **Very Good** | **Recommended for continuation with specific focus** |

Specific Recommendations:

|  |
| --- |
| **Despite of their score in programme delivery,**   * **All the staffs should maintain and update diaries.** * **All 18615 active population was reported as newly registered** * **STI referrals to govt. and PPP clinics to be started again** * **PM, M&E and Counsellors should start maintaining diaries as per monthly plans.** * **The office of the TI is being used for minimum of 3 projects** * **Field Sessions are reportedly conducted exactly as per budget every month as 10+20 for the past 2 years looks unrealistic.** |

Name of the evaluators Signature

|  |  |
| --- | --- |
| Mathivanan R |  |
| Purvi Trivedi |  |
| Shailesh Patil |  |