Annexure: B

Reporting Format- B

Structure of the Detailed Reporting Format

(To be submitted by evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

- Background of Project and Organization

Network of Pune by People Living with HIV/AIDS(NPP+)  started the Intervention for Prevention of HIV among the Migrants during August 2010. The Project is implemented in the Chinchwad industrial area as well as the surrounding areas where large scale constructions are going on.  The target for the project for coverage is 15,000 where as the project is able to register 13,672 migrants for intervention.  There is one Project Manager, One Counselor, One M&E cum Accountant and Eight ORWs. The project is also using the services of local Medical Doctor’s for its health camps.  Project has set up two DICs in project locations.  The third DIC serves as office for the project. The intervention of the project is for target audience namely Construction Laborers and the Industrial workers

- Name and address of the Organization

NETWORK OF PUNE BY PEOPLE LIVING WITH HIV/AIDS

Address:

424, New Mangalwar Peth, Samaj Kalyan Building. Opp: ICDS Office, PUNE 411 011

- Chief Functionary

Mr. Sanjay Jadhav

- Year of Establishment

April- 2004

- Year of month of project initiation:

August 2010 and re-contracted with revised indicators and approach from August 2011 to 2016

- Evaluation Team:

Mr. Sagar Karmakar (Team Leader), Ms. Prabha Jadhav (Co-Evaluator), Mr. Babasaheb  Vidyagar (Finance Evaluator)

- Time Frame:

16th to 18th April, 2016

Profile of TI

(Information to be captured)

- Target Population Profile: MIGRANTS

- Type of Project: Bridge Population

- Size of Target Group(s): 15,000 Migrants

- Target Area: Bhosari,  Landewadi,  Bhosari Gavthan,  Alandi,  Khandobamal,  Sadgurunagar

Key findings and recommendation on Various Project Components

- Organizational support to the programme -:

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

Network of Pune by Positive People has been working in the area of providing psycho-social support to people living with HIV/AIDS in the district.  The Organization has established its branches in the form of Taluka level network in all the 13 talukas of the district, among them two of the networks are already registered as independent Organizations. This CBO started implementing Projects independently.  The Board members are able to provide support to the Migrant project supported by the MSACS, as and when required. The Treasurer of the CBO Mr. Sanjay Jadhav is the Project Director of the project.

- The Project Director and the Project Manager need to train the staff members on Basics HIV/AIDS/STI/Condom and other critical inputs

- Project Director needs to Monitor the work of the Project Manager and Team

- Organizational Capacity:

- Human resource: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover.

The NPP is a CBO with experience and ability of working with positive people in the District.  This organization has a standing for providing good support to the migrant project.  The Migrant Intervention project is implemented in an important area where influx of migrants to the area is considerable.  In order implement this intervention, the organization has recruited all the staff as sanctioned in Project.

PD>PM>Doctor>Counsellor>ORWs (8)> PLs (20)

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

The project Manager is trained in HIV/AIDS as well as the new strategies of the Migrant intervention. The CBO has experience in the field of working with positive people.

| Sr No. | Date | Organized by & Venue | Topic | Type of Participant | No. of Participant | Duration | Methodology | Name of resource Person |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 10/11/14 to 13/11/14 | STAPI | Induction | PM | 1 | 4 Days | Participatory Lecture & Role Play | STRTC Team Deepak Nikam |
| 2 | 27/11/14 to 29/11/14 | STAPI | Induction | Counselor | 1 | 3 Days | Participatory Lecture & Role Play | STRTC Team Meera Limaya & Roshan Maisar |
| 3 | 20/12/14 | MSACS | IBBM | PM, Counselor | 1 | 1 Days | Participatory Lecture & Role Play | IBBM Team |
| 4 | 26/12/14 to 27/12/14 | STAPI | Induction | Counselor | 1 | 2 Days | Participatory Lecture & Role Play | STRTC Team |
| 5 | 27/1/15 to 29/1/15 | STAPI | Induction | PM, M&E | 1 | 3 Days | Participatory Lecture & Role Play | STRTC Team Deepak Nikam |

- Infrastructure of the organization

Organization has all basic infrastructural facilities required for the effective implementation of project.  There are three DICs of which one is serving as the project office. One of the DICs set up in the project area in Sadgurunagar & Second of the DICs set up in the project area in Landewadi.  The project office has required equipments like computer, table, TV, VCD, PA system and IEC aids etc.

- Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

The project staff especially the PM, M&E cum Accountant Officer and Counsellor should be provided with more basic and functional trainings from various agencies. The project team follows SACS prescribed formats and tools. Documents have been maintained by the project staff and some marginal gaps were found in the same. Form A, B1, C, C1, D, E were maintained and updated. Micro planning was done properly, therefore the impact of the project deliverables were easy to measure. The documents related to screening and referrals have been maintained.

- Programme Deliverables

Outreach

- Line listing of the HRG by category

25519 were line listed as on 31 March 2016. The HRG register (Form E) is maintained and updated regularly.

- Registration of migrants from 3 service sources i.e.STI Clinics, DIC and Counseling.

Registrations are witnessed in the above mentioned 3 service sources.

- Micro planning in place and the same is reflected in Quality and documentation.

Hotspot analysis, Peer map, Service map and preference ranking was done in a proper way but needs to be done with more perfection. Micro planning in place and the same is reflected in Quality and documentation. A very basic micro level plan was in place, but quarterly updating of the same was also done on the regular basis.

- Outreach planning-quality, documentation and reflection in implementation.

There are 20 Peer Leaders who are parts of the outreach strategy of the project with a ratio of 1 PL: 850. It is found that the ORWs are conducting group sessions and individual sessions in the work areas and congregations for a better reach out. From the discussion with the community members the same can be found.

- PF: HRG ratio, PE: migrants/truckers.

PL: Migrants = 1: 850

- Supervision-mechanism, process, follow-up in action taken etc.

The project team using SACS prescribes formats and tools for internal supervision and the impact was seen. Monthly and weekly meetings, records and the needed documentation need to be triangulated properly for supervision and follow up action by the team.

As there is a specific outreach plan in place the supervision process becomes easier to follow. The same has been reflected in the following:

- Services

- In case of migrants and truckers the STI drugs  are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with the use of revolving funds.

The procurement system is shown in the project and quality drugs are also available.

- Quality of treatment in the service provision-adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC, ART, DOTS centre and community care centers.

The project has a good rapport with the ICTC, ART, DOT, CCC etc.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents  reflecting  presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting officials documents in this regard.

Proper documentation of referral slips and registers is in place with the TI. Stock register is maintained and system of procurement of medicines are as prescribed by NACO/MSACS.

- Availability of condoms- Type of distribution channel, accessibility, adequacy etc.

Condom Social Marketing is done in the project

- No. of condoms distributed through outreach/DIC.

3950

- Information on linkages for ICTC, DOT, ART, STI clinics.

Migrants need to be more informed on linkages for ICTC, DOT, ART, STI Clinic etc.

- Referrals and follows up.

Referral and follow-up part is quite satisfactory. Cross verified with ICTC centre with referral slips.

- Community participation:

- Collectivization activities: No. of SHGs/Community groups/CBO’s formed since inception, perspectives of these groups towards the project activities.

No community member is included in any kind of committee formed by the project. No evidence of any SHG, CBO or other community groups.

- Community participation in project activities-level and extent of participation, reflection of the same in the activities and documents.

Most of the community members are not aware about the DIC activities and types of service delivery, DIC and its concept.

- Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB, clinics etc…

The TI is linked to most of the services with proper coordination and follow-up was found.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

Total 431 populations were tested for HIV out of 15,000 populations.

699 community members were referred and out of them 431 were tested

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

The stakeholders need to be oriented about the project activities. No stakeholders were fully informed about the services.

Proper stakeholders analysis and power mapping was not done properly. The directory of services/referral directory needs updating on time-to-time basis. The project team needs proper guidance in this regard.

- Financial system and procedures

- System of planning: Existence and adherence to NGO-CBO guidelines/any approved systems endorse by SACS/NACO-supporting officials communication.

The system of planning is not followed as per NACO guidelines.

- Systems of payments -  Existence and  adherence  of payments endorsed  by SACS/NACO, availability and practice of using printed and serialized vouchers, stock and issues registers, practice of setting of advances before making further payments.

The vouchers are not preprinted and serially numbered. None of the registers are properly documented. M&E salary paid to the person whose name not in the attendance register and the same as been documented with sign in the salary register. Two DIC rent are paid in cash of Rs.10000/- each. The closing cash balance in hand is Rs.21000/- which is not carried forward in the next financial year, and the same is not reflected in tally software package.

The staff salary cheque is bounced.

- Systems of procurement – Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

The three quotation system is followed for fixed assets. The medicines not procured.

- System of documentation- Availability of bank accounts (maintained jointly, reconciliation made monthly basis), audit reports.

TI is maintaining separate bank account and it jointly operated by two signatories. Bank reconciliation is not made on monthly basis. The Audit is been done for the year 2014 -2015.

- Competency of the project staff.

VII a.  Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

The Project Manager is with NPP+ since the beginning of the project. She is qualified professional social worker with 7 year of experience with health and development. The PM needs to be more focused on outreach planning as well as implementation

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc.

The counselor is a graduate have the experience in working with the Migrant community. He needs to be more oriented in his job and in delivering services to the community.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis,STI symptoms, importance of RMC and ICTC Testing, Support to PEs, field level action based on review meetings etc.

ORWs lacks in basic information about HIV/AIDS. They also lack in knowledge about their target on various indicators for their PEs . Outreach activities are not also done properly. ORWs need to be more oriented in hotspot analysis, importance of various testing like ICTC, RMC, STI etc.

VIII g. Peer educators in Migrant Projects.

Whether the peers represent the source States from where maximum migrants of the area belong to, whether they are able to priorities the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condom, able to plan their outreach, able to manage the DIC’s/health camps, working knowledge about symptoms of STI, issues related to treatment of TB, service in ICTC & ART.

Out of 20 PLs, 5 of them are source State from where a number of migrants belong to. They are quite aware their work type, residence, high risk activities etc. The PLs are not that much competent in condom demonstration and in delivering other services.

VIII j. M&E Officer

Whether the M&E officer (FSW & MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical  information  about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

The project has a post of M&N cum Accountant.

IX b. Outreach activity in Truckers and Migrant Project

Interact with all PES and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in services uptake that is whether enough clinic footfall, counseling is happening. Whether the stake holders are aware of the outreach sessions.  Whether the timings of the outreach sessions are convenient/appropriate for the truckers/migrants when they can be approached etc.

It seems that the outreach sessions are not up to the mark. Clinic footfall and counseling is happening but not that much effective one. Stake holders are not that much oriented or informed about the project and its services. Though the timings of the sessions seems to be convenient when the migrants can be approached. The target community has expressed their satisfaction over the mid-media activities and the awareness sessions conducted in the projects site. It is also found that the Clinical services provided though the site level programs.

- Services

Overall services in the project, quality of services and service delivery, satisfactory level of HRG’s.

The service delivery is ensured by the TI. Improvement and involvement of stakeholders at all levels needs to be done. Some group activity may be brought in to place in order to have second line representation among the community members.

- Community involvement

How the TI has positioned the community participation in the TI, role of community in planning implementation, Advocacy, monitoring etc.

Proper advocacy needs to be done for effective community involvements. The role of the community is asking community contribution and functional ownership in addressing various factors involved in transmission of HIV and other blood borne infections among IDUs and their sub-groups.

- Commodities

Hotspot/project level planning for condoms, needles and syringes. Method of demand calculation Female condom programme if any.

The TI has developed non Traditional outlets. In the new revised program there is no provision of commodities like medicines, Condom etc. only rolling funds were provided for condom procurement, which they have utilized. But condom social marketing is not up to the mark.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy, networks and linkages, community  response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

The Project has taken initiative to involve stakeholders in the project.  Advocacy Programmers  are conducted by the project. No commendable effort is made so far by the project for strengthening of the project management committee or site level committees.

- Stake Holders Analysis is required to be done

- Advocacy plan has to be done soon after the analysis

XIV. Social protection schemes/innovation at project level HRG availed welfare schemes, social entitlement etc.

There are no special efforts made by the project on providing Social Protection Schemes to the target community.

XV. Best Practices if any.

- Project has been taking initiatives of conducting meeting of different NGOs involved in HIV/AIDS  programmes

- Staff members are provide with an apron to wear in the work site for an easy identification of the intervention.

Annexure C

Confidential  	                                               Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Sagar Karmakar (Team Leader) | 25/6/B, Jogenrda Basak Road, Baranagar, Kolkata-700036. Mail Id: sagar.karmakar@gmail.com Mobile: 98367 56564 |
| Ms. Prabha Jadhav (Co-Evaluator) | Mail Id: prabha.agale@gmail.com Mobile:9373032369 |
| Officials from SACS/TSU (as facilitator) |  |

| Name of the NGO: | NPP+ |
| --- | --- |
| Typology of the target population: | Migrant |
| Total population being covered against target: | 25519 against 15000 |
| Dates of Visit: | Bhosari, Pune, Maharashtra |
| Place of Visit: | 16th to 18th April, 2016 |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 41%-60% (57.6%) | C | Average | Recommended for |

Specific Recommendations:

The TI does not qualify in the finance part, scored only 30.8% (marks obtained 4 out of 13)

Name of the Evaluators 						Signature

| Mr. Sagar Karmakar (Team Leader) |  |
| --- | --- |
| Ms. Prabha Jadhav (Co-Evaluator) |  |
| Mr. Babasaheb Vidyagar (Finance Evaluator) |  |