Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of the NGO

Veshya AIDS Muqabala (Anyay Mukti) Parishad, Sangli.

Review report - VAMP TI 1

Dated 22 & 23 April 2016

VAMP or Veshya Anyay Mukti Parishad, is sex worker collective consisting of 5,511 women in sex work in Maharashtra and North Karnataka. Since 1990, they have been working on issues of health and human rights of sex workers. VAMP plus is the off shoot of VAMP and has HIV positive sex workers. VAMP plus aims to motivate sex workers living with HIV to access ARV treatment, ensure nutrition and adherence. In addition VAMP plus engages in advocacy with health officials and government officials to access health and welfare schemes.

VAMP was set up with the aims of forging and consolidating a common identity among women in sex work, empowering them to assert their rights and protect themselves from HIV infection. By functioning as a collective, VAMP is able to attract members in the sex worker community. Membership is not formalized; any woman in sex work who utilizes VAMP’s services or gets involved in the activities becomes a member. VAMP has a hierarchical structure depending on responsibilities and roles accorded to members. Collective meetings decide changes in this structure and the roles of members elected to various posts. VAMP’s board members started as peer educators, who know the pulse of the community.

VAMP emphasizes that a peer educator’s portfolio spans the entire continuum of HIV: before, during and after infection. Their preventive work on HIV/AIDS is mainly through peer education, condom distribution and assisting sex worker colleagues who have sexually transmitted infections and other health problems to access medical help. VAMP women play a supportive role when community members become HIV infected. Often peer educators become the de facto families and care givers of ill colleagues. Not only do they ferry these women back and forth from hospitals but they also organize food for them, look after the women’s children or even lovers who could be sick as well and offer unconditional support. When a colleague succumbs to AIDS related health complications they take responsibility of the funeral arrangements.

While HIV/AIDS is a key focus area in VAMP women’s initiatives to help themselves, considerable attention is also given to the socio-economic impact of sex workers’ health and wellbeing. VAMP plays a crucial role in promoting the interests of its constituents, by mediating community disputes, lobbying with the police, helping colleagues’ access government systems and services and facilitating leadership potential among its members.

However, this does not mean that all VAMP members are able to confront and challenge police harassment. More women have become aware of their rights and recognize that they have the capacity to negotiate with others, including those in authority, to diffuse threatening situations. No longer are they told by others about how to act, they are empowered to resolve issues through the Mohalla grievance committees. These committee meetings are held every week and help resolve community disputes that range from problems with exploitative brothel owners, anti – trafficking measures to infighting within and between brothels.

VAMP works with the overall goal of improving the quality of sex workers’ lives through the following –

- Advocacy with community members, leaders, local political leaders, police, policy makers, NGOs.

- Training of trainers – organizing workshops, exposure visits.

- Education - rights of people in sex work.

- Production of plays, documentary films and use of electronic media, use of rallies.

- Community led research study planning and implementation.

- Participation at local, national, international level-meetings, sessions, debates, dialogues and conferences on HIV/AIDS, sex worker rights and policy.

- Name and address of the Organization

Sangram Sanstha , VAMP 1 office Sangli  
                                Behind Parswanath English Medium School ,

Balaji Nagar , Kupwad Road , Sangli ,Pin code – 416416

- Chief Functionary:  Ms. Chanda Vajane  (PD)

- Year of establishment:

Founded in 1990

- Year and month of project initiation:

Project is running from  April 2012

- Evaluation team

Mrs. Seema Anil Kumar  (Team Leader)

Mr  Sagar karamakar  (Co evaluator)

Mrs.  Mulla  ( DAPCU Finance evaluator)

- Time frame

22nd  23rd  and 2nd    April/ May 2016

Profile of TI

- Target Population Profile: FSW (900)

- Type of Project:  Core

- Size of Target Group(s) – 890 FSW (active population)

- Sub-Groups and their Size

FSW

Brothel based	:  595

Street based: 167

Home Based                        : 128

- Target Area

Sangli  Gokul Nagar  and Surrounding area

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

- The organization support to the programme is very good and the PD and few governing body members support the intervention.

- The chief office bearers and the general members are participatory and active in the implementation of the programme and addressing crisis issues.

- It was found that the PD mark her presence in the all review meetings conducted.

- During the time of visit the team got to meet some of the GB members along with the PD and it seemed that the group is leading the TI team with support and capacity.

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

TI Project staff patterns		:

Project Director			:	01

Project Manager		:	01

M & E cum Accounts                     :	01

Doctor                                             :              01

Counselor			:	01

ORW				:	04

PE				:	15

- Below is the staff list which reflects the name, designation and qualification of the individuals employed with the TI.

| Sl # | Names | Designation | Qualification | Age | Date of join |
| --- | --- | --- | --- | --- | --- |
| 1 | Chanda Wajane | PD | Not literate | 45 | 01/04/2012 |
| 2 | Mahesh Manoji | PM | 10 th Passed | 28 | 01/01/2013 |
| 3 | Kavita Mali | Counsellor | 12 th Passed | 32 | 01/06/2015 |
| 4 | Neeta Jog | MEA Officer | B. Com. | 49 | 01/07/2015 |
| 5 | Dr. Samuel Ranbhise | Doctor | M. B. B. S. | 52 | 01/09/2015 |
| 6 | Deepak Modi | ORW | 10 th Passed | 30 | 01/04/0214 |
| 7 | Sangita Manoji | ORW | 8 th Passed | 29 | 01/04/2012 |
| 8 | Bismilla Shaikh | ORW | Not literate | 35 | 01/04/2012 |
| 9 | Meena Barke | ORW | 9th Passed | 38 | 01/04/2012 |

- The organization has recruited only one professional and most field level workers are from the community itself.

- The organization follows SACS – NACO norms for staffing pattern.

- Project team follows the reporting structure laid down by NACO- SACS and they maintain the documentations for the same.

- Documents for staff level supervision available and the documents for management level supervision were available with the project team.

- The organization has given space for the leadership to develop and it was evident that they are indeed leading the project in respective areas.

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

- Only 5 in-house trainings taken by the project staff .

- Thematic trainings are suggested for both staff and PEs to name a few would be:  technical documentation, micro planning, Advocacy from concept, planning to implementation.

- No training need assessment done by the TI and no impact assessment of the training has been done so far.

- Infrastructure of the organization

- The project office has been shifted to Sangram Office in Sangli district due to budget cut which was evident.

- Office furniture and computer available in the project office and the requirement of the same has been fulfilled by the organization according to NACO – SACS norms/needs.

- No Seprate counselling room as 2 TIs are under one place .Most of the counselling is done in the field settings

- Clinic found in the DIC of Gokul Nagar.

- It was learnt that the PPP has got decent clinic set up and check up is done by only verbal interactions and it is only when the HRG complain of severe symptoms the TI send them to the specialists and the expenses have to be borne by the individual FSWs.

- Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of  documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

- Team’s approach towards documentation is encouraging and the evaluation team has found  no limitations in the area of documentation.

- The counseling register requires to be filled up properly. And to maintain ART data properly. The counselor understands the basics of counseling.

- It was understood that most ORWs are from the community and they feel hard to understand English at times. The evaluating team feels the requirement of Marathi/ Hindi or convenient language for the ORWs to understand.

- Form B is reflecting the risk assessment and vulnerability issues but the same requires periodical updating.

- Review meetings are conducted to discuss the achievement of the targets set in indicators. The documentation and reporting system has been monitored.

- Few PEs are known to be illiterate so the organization developed pictorial outreach and micro-plans for their convenience.

- Most of the concepts of project documentation are clear with the team.

- Hot spot analysis is done for individual hotspot to plan service delivery.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

- A total of 1775 individuals have been line listed by the project staff. This includes 890

Brothel base – 595   , Street base – 167, Home base -128

- During the interacting with the PE it was found that the individual the PE is tracking exceeds the number of active population given by the TI.

- Micro planning in place and the same is reflected in Quality and documentation.

- Micro planning in place but followed unevenly by the project staff and the PEs.

- The TI has done hot spot analysis of each and every hotspot to strategize outreach activity.

- The project staff has their plans in place, but ORWs are the ones who follow micro planning.

- Micro-planning in place and it reflects in quality and documentation but the same require improvement and to be reviewed after a given period after mapping the vulnerability of HRGs.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

- A total of 1775 individuals have been line listed by the project staff. This includes 890  FSW (  Street based:595, Home Based : 128 and Street  based : 167)

- 890 active FSW’s are covered by the Project staff.

- As per the records made available, regular contacts (twice in a month) are 890  FSW’s and 890 once in a month with FSWs.

- Outreach planning – quality, documentation and reflection in implementation

- Outreach planning done on a very basic level.

- ORWs put their efforts in documentation which is fairly visible but some gaps as mentioned above do exist.

- The understanding towards documentation is very good among the personnel.

- The ORWs has got good understanding of Form A and D and it has been filled properly.

- Form A does have the movement status of the HRGs and they have recorded the contact number of any individual HRGs.

- PE: HRG ratio, PE: migrants/truckers

- PE; HRG ratio 1:60 is fairly maintained as it seems by the number of PEs they employed. But physically it was found that the HRGs are evenly distributed among the PEs as all the  PEs delivering services HRGs.

- Regular contacts ( as contacting the community members by the outreach workers / PEs at least visit the HRG twice a month and are providing services such as condoms and other referral services for FSW – Understanding among the project staff has got its reflection in impact among the community members

- The staff has a good understanding of regular contacts, registered contacts and reached contacts at ORW level.

- The PEs meet HRGs every day and ORWs also contact in the field every day .

- Community of HRG is been provided condom in these visits and are referred for HIV and RPR tests if necessary and as per the schedule.

- ORWs and PE track individual HRG for service provisioning and refer them when they are due or overdue.

- Documentation of the PE education

- Peses are either semi literate or illiterate.

- PEs do not have basic understanding about the documentation.

- The PEs mostly remember the numbers of commodity distributed and name of the HRGs met which is shared to their respective ORW in charge and thus the team is skeptical about the quality of the document collected.

- ORWs help PEs to complete their documentation.

- Quality of PE education- messages, skills and reflection in the community

- PEs are very vocal and clear when they communicate though require more capacity.

- PEs have got a good knowledge and their involvement in the project is remarkable.

- The PEs are a group of illiterate or semi literate people who require ORWs help to do the documentation.

- Most of the community members are satisfied by the services provided by the PEs.

- 50% of the PEs met are above the age group of 30, 4 are below 30 and 5 are above 50 yrs of age.

- Supervision- mechanism, process, follow-up in action taken etc

- Supervision is done at two levels first at ORW level and second at PO level.

- The PD is understood to make field visits and he signs in required document of TI.

- Proper documentation for supervision process is followed by the project.

- Minutes of the meeting available with the project staff for looking into follow up action taken by the management for any specific task assigned.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

- STI service is delivered through PPP linkages and the TI conducts RMC, screening and treatment in makeshift clinics in the bars where the HRG operates.

- RMCs were done regularly with the HRGs.

- It was understood that all RMC’s are done by the PPP.

- The quality of RMC though is understood to be poor as there is no clinic set up for the HRG to get screened properly. RMCs are done based on interviews and by asking symptoms. In some specific cases when the symptoms are serious the TI send the HRG to other facilities.

- Quality of the services- infrastructure (clinic, equipment etc) location of the clinic, availability of STI drugs and maintenance of privacy etc.

- The STI services are provided through PPP who is a BHMS and he has been trained for syndromic management.

- The static clinic has its setbacks as well because the bar has got very little space to offer as they have got very little place to offer where the TI may conduct screening and RMC ensuring the privacy and confidentiality of the HRG.

- The evaluation team is also skeptical of related issues like waste management, sterilization, self protection and usage of speculum in such poor facility.

- STI drugs were made available to the community.

- It was learnt that the medicine stock is distributed by the TI as prescribed by PPP’s. It was understood that the TI ran out of STI medicine stock and in that case the HRG were provided with prescriptions only and in few cases the TI helped procure free medicines from the doctor’s free sample.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centers.

- RMCs are evidently been done regularly as the documents provided reflects.

- There are referrals to ICTC and STD clinic in Govt. set up for RPR and HIV testing. They have been collecting blood samples from the HRGs  during the camps .

- They have referred very few FSWs in ICTC and as a result the knowledge about ICTC facility has not got translated to the population.

- During a visit to the ICTC it was noticed that the TI never referred HRG most of the checked in the camp of April ’ 15 and then on until March ’ 16 they 688 HRGs and twice 403.

- Medicines are distributed from clinic and stock register for the same maintained. The TI was out of stock for the STI medicine.

- Referrals were done and the TI followed up whether certain HRG reaching out for service or not.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- Documents and record keeping is a real issue with the TI and the necessary documents has been maintained properly.

- Documents are maintained as per NACO- SACS guidelines, lack of understanding for the same is found with the project staff.

- Referral slips are found to be properly filled up.

- Follow up cards are found.

- All CIF forms, Drug stock register were available at the NGO office.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

- The TI has got no condom stock in hand.

- No condom depots or linkages are established by the project staff.

- Condoms are distributed through PEs and ORWs evidently.

- There are no condom outlets formed by the TI.

- During the project period from April 15 to March 16 the staff and the PEs have distributed 581010 condoms in the community against the demand of 952660	 condoms.

- The project has distributed very few condoms through CSM when there were no govt. condoms available.

- Female condom is not there in the project.

- Information on linkages for ICTC, DOT, ART, STI clinics.

- Project has linkages with the existing govt. infrastructure for STI and allied services.

- A rapport with the local govt. hospital and its STI centre, ICTC and ART centers has been maintained. The TI require more rapport to be established and require referring HRGs to the ICTC and allied services other than only relying on its own centers as referrals will help the sustainability of project objective and the health seeking behavior will develop.

- Referrals and follows up

- The project focus on referral is not encouraging as they rely more on services they can avail. As a result the sustainability by linking the community with available services is getting effected which is detrimental to the  objective.

- Lack of Conceptual clarity within the field team and uneven planning may have a direct impact on the follow up part of the STI care component of the project, but follow-up of clients for the service is evidently good.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- It was understood that the organization formed their own CBO with the community.

- The organization is itself a CBO and they have taking ownership of the project.

- It was understood that the FSWs/MSM/TG community is still under the fate of the brothel owners, They require doing lot of things as a compulsion or to be in the good book of the owners. And it seemed that they are not fully empowered enough to deny anything they are not comfortable with.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community participation is holistic and the TI has engaged all field personnel from the community itself except few technical persons.

- Most project personnel represent the community.

- Documents reflect the participation of the community members in events organized by the project team.

- It was not understood to what extent the HRGs avail the DIC services as during the evaluation the team found no HRGs visiting the DIC for any purpose.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- The TI has got linkages with ICTC and FICTC in the PHCs .

- The TI though referred and linked all positive HRGs with the ART facility but follow up is very poor.

- During the visit no Civil Hospital was visited but it was understood from the discussion with the HRGs that they do not seek health services from Govt facilities and they do rely on the services that were brought to their door step by the organization.

- It was understood that the footfall of the HRG in the service facilities offered by CH is very poor.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

- Almost 80% of the line listed HRGs have been tested for HIV for at least once in the last 12 month.

- The data collected from sources do signify there are but bit discrepancy and as there are no data available with the TI to find the differences between referred and actual reached the team has to assume that the total population never reached the service facility.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- They have got strong linkages with ICTC, ART and STI clinic. The HRGs referred to the service providers are dealt in priority.

VII. Financial systems and procedures

- Systems of planning  :  All Employee Weekly Work Plan fixed in Weekly meeting and get oral approval from PM

- Systems of payments-In System of Payments some week points. Some cash transation is done above given limit of Rs.2000/-. Some times Peers or other employee salary also paid by cash.

- Systems of documentation- Systems of documentation is good

- General: -

- Suggestions:- All transation is done by Cheque. Vouchers get with numbered.

VIII. Competency of the project staff

VIII a. Project Manager

Mrs. Chanda Vajane          Educational Qualification: Not literate

The PROJECT MANAGER is not technical person but who has been with Sangram for long time and she is from the community .

- She is good in field work but no technical knowledge.

- Technical inputs recommended are:  knowledge about program performance indicators, mentoring and field visit & advocacy initiatives etc.

- She requires monitoring the project activity and analyzes data and authenticating the validity of the same which is not possible .

- VIII b. Counsellor

Mrs.  Kavita Mali ,                             Educational qualification-  12th pass

- She has got fair understanding about the counseling.

- Her understanding about the basics of HIV/AIDs and STI is clear though.

- The documentation of the counselor required to make authenticated and justified.

- The counselor has been found to document that she is counseling for component like risk assessment, risk reduction, condom use, HIV, STI and other issues every time she meets an individual HRG and all the counseling took her 10 min only.

- It seems that she had planned BCC activity for the individual HRG.

- The Counselor was found to be popular among the HRGs .

VIII c.

M&ECum Accountant                                        Education Qualification : B.com

Mrs. Nita Jog

VIII d. ORW

Mr. Deepak Modi  ,                                  Educational Qualification: 10th

Mrs. Sanjeeta Manoji                               Educational Qualification: 8th

Mrs. Meena Barke ,                                   Educational Qualification: 9th

Mrs. Bismilla Shaikh                                  Educational Qualification : Non Literate

- All the 4 ORWs are from the community.

- The ORWs clarity about risk assessment requires enhancement.

- They have very basic knowledge on various targets, outreach plan, STI symptoms, importance of RMC and ICTC testing .

- They share a good rapport with their PEs.

- ORWs are aware and confident about field level situation which is a great sign.

VIII e. PE educators

- They have knowledge on importance of RMC and ICTC testing.

- Excellent communication skills among the PEs though few PEs are timid.

- Demonstration skills require improvement.

- Knowledge on symptoms of STI, knowledge about service facilities etc is good.

- The PEs are quite involved in the project and the TI requires to ensure greater involvement of the PEs in the intervention.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs.  Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- The PEs and ORWs conduct regular session with the HRGs and it is evident that the population is indeed going to the facilities.

- Service uptake is yet to be spontaneous as services are carried to the operational point.

- Most of the hotspots are very far so outreach is not possible at every point of time as distance is a issue. They need to plan outreach keeping in lieu the distance and availability issues.

- Outreach monitoring need to be more frequent.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- Overall the community seems to be satisfied by the services provided by the project team.

- The TI got a good referral and linkages system with Govt. STI clinic, ICTC and ART but poor service uptake by the HRGs have been witnessed except the Art where all detected positive HRGs linked but the number attended ICTC is very poor as the TI.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- Community involvement very good to service provision and community events at project level only.

- Much work needs to be enhancing the crisis management and advocacy efforts.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes.  Method of demand calculation, Female condom programme if any,

- ORWs plan condom gap analysis which is a good sign.

- The team has a system for demand calculation, which now needs to be percolated towards PEs.

- The project team interviewed all FSWs and got to know that they are all using condoms but they have not tried to evidently bring into book the source of condom.

- No female condom programmes in place. According to outreach staffs the FSWs find it inconvenience using FC and it was reportedly having got complexities.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

- Conceptual clarity for advocacy component needs to be imbibed in the project team as organizational management is very strong.

- Crisis committee in place but participation of different stakeholder in the same needs to be ensured.

- Linkages and networking with the Govt. facilities and other organizations are evidently there but the poor service uptake by the HRGs as the organization bringing all facilities to the doorstep which in larger dimension is depreciating the progress of sustainability in linking the HRGs with Govt. facilities.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes,  	social 	entitlements etc.

- Social Entitlement

- Voter Cards					:  16

- Ration Cards					:  07

XV. Best Practices if any

- HR policy is in place .

Annexure C

Confidential                                                                                                                      Reporting form C	        EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mrs. Seema AnilKumar (Team leader) | 9833582268 e-mail: seemanil@gmail.com |
| Mr. Sagar Karmakar (co-evaluator) | 9836756564 e-mail : sagar.karmakar@gmail.com |
| Mrs. Mulla (DAPCU Finance Evaluator) | e-mail : dposangli@mahasacs.org |

| Name of the NGO: | VAMP 1 ,Sangli |
| --- | --- |
| Typology of the target population: | FSW |
| Total population being covered against target: | Target- 900Covered- 890 |
| Dates of Visit: | 22nd 23rd April 2016 |
| Place of Visit: | Sangli , Maharashtra |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 78 % | B | Good | Recommended for continuation |

| Total Score Obtained in % | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 40% - 60% | C | Average | Recommended for |
| 61% - 80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning site |

Specific Recommendations:

- Thematic trainings are suggested for both staff and PEs to name a few would be: technical documentation, Advocacy from concept, planning to implementation. - The PROJECT MANAGER requires enhancing knowledge on project planning and making use of available financial resources. - Condom linkages and Condom social marketing required to be linked and enhanced. - The organization requires monitoring frequently by the PO from technical support units. - Need to Check ART data and follow up should be done regularly

Name of the evaluators				Signature

| Mrs. Seema Anil Kumar Team leader) |  |
| --- | --- |
| Mr. Sagar Karmakar ( Co-Evaluator) |  |
| Mrs. Mulla ( DAPCU Finance Evaluator) |  |