## Sheet1
NATIONAL AIDS CONTROL PROJECT-III
Procurement Plan for the year 2009-10 (Equipment and Goods)
Pooled Fund - As on May 15, 2009
S. No. | Items | Method of procurement | Unit | Quantity to be procured (Nos.) | Unit Cost (Rs.) | Estimated Value (in Rs. Crore) | Estimated Value (Million USD) | Preparation of Specifications and Bid Document | No Objection of Bid documents by the World Bank | Publication of IFB in Newspapers and UNDB/ dgMarket and beginning of sale of bid document | Receipt and Opening of Bids | Submission of BER to Bank for No Objection | Receipt of No Objection of Bank for BER | Issue of contract award notice | Signing of the contract | Delivery to start by (date) | 100% delivery complete
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A) Diagnostic Kits
1 | HIV (Elisa) | ICB | Tests | 4637088 | 6 | 2.7823 | 0.66244 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
2 | HBV (Elisa) | ICB | Tests | 4612128 | 8 | 3.6897 | 0.8785 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
3 | HCV (Elisa) | ICB | Tests | 4637088 | 9 | 4.1734 | 0.99366 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
4 | HBV (Rapid) | ICB | Tests | 1092480 | 7.5 | 0.81936 | 0.19509 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
5 | HCV (Rapid) | ICB | Tests | 1092480 | 16 | 1.748 | 0.41618 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
1 | HIV (Rapid) | ICB | Tests | 1092480 | 8 | 0.87398 | 0.20809 | already done | already done | already done | 2009-05-18 | 2009-05-30 | 2009-06-07 | 2009-06-15 | 2009-06-30 | 2009-08-01 | 2010-08-31
| Sub-Total |  |  |  |  | 14.0866 | 3.354
B) Equipment
1 | Blood Transportation Vans | ICB | Nos. | 250 | 500000 | 12.5 | 2.9762 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
2 | Blood Transportation Boxes | ICB | Nos. | 1000 | 100000 | 10 | 2.381 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
3 | Blood Mobile Vans | ICB | Nos. | 32 | 7500000 | 24 | 5.7143 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
4 | Refrigerated Centrifuge | ICB | Nos. | 32 | 750000 | 2.4 | 0.57143 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
5 | Blood Bank Refrigerator (300 bags capacity) | ICB | Nos. | 937 | 125000 | 11.7125 | 2.7887 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
6 | Deep Freezer (-40 deg C ) | ICB | Nos. | 21 | 300000 | 0.63 | 0.15 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
7 | Deep Freezer (-80 deg C) | ICB | Nos. | 21 | 300000 | 0.63 | 0.15 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
8 | Platelet Agitator & Incubator | ICB | Nos. | 17 | 150000 | 0.255 | 0.060714 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
9 | Sterile Connecting Device | ICB | Nos. | 21 | 1000000 | 2.1 | 0.5 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
10 | Cell Counter | ICB | Nos. | 18 | 400000 | 0.72 | 0.17143 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
11 | Coagulometer | ICB | Nos. | 21 | 120000 | 0.252 | 0.06 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
12 | Laminar Air Flow Bench (Bio-Safety Cabinet) | ICB | Nos. | 18 | 200000 | 0.36 | 0.085714 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
13 | Donor Couch | ICB | Nos. | 88 | 100000 | 0.88 | 0.20952 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
14 | Bio-Mixer | ICB | Nos. | 88 | 100000 | 0.88 | 0.20952 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
15 | Di-electric Tube Sealer | ICB | Nos. | 38 | 120000 | 0.456 | 0.10857 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
16 | Plasma Thawing Bath | ICB | Nos. | 21 | 110000 | 0.231 | 0.055 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
17 | Cryo Bath | ICB | Nos. | 21 | 150000 | 0.315 | 0.075 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-10-01 | 2009-11-30
| Sub-Total |  |  |  |  | 68.3215 | 16.267
C) Blood Bags
1 | Single Blood Bags (350 ml) | ICB | Nos. | 4179500 | 45 | 18.8077 | 4.478 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
2 | Double Blood Bags (350 ml) | ICB | Nos. | 513700 | 65 | 3.339 | 0.79501 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
3 | Quadruple Blood Bags (SAGM) (350 ml) | ICB | Nos. | 1306900 | 110 | 14.3759 | 3.4228 | 2009-04-20 | 2009-04-30 | 2009-05-07 | 2009-06-25 | 2009-07-10 | 2009-07-15 | 2009-07-20 | 2009-08-05 | 2009-09-30 | 2010-08-31
| Sub-Total |  |  |  |  | 36.5227 | 8.6959
D) Color Coded Drug Kits
1 | Kit 1 | ICB | Nos. | 1105994 | 31.5 | 3.4839 | 0.8295 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
2 | Kit 2 | ICB | Nos. | 1391864 | 11.5 | 1.6006 | 0.38111 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
3 | Kit 3 | ICB | Nos. | 448491 | 36.5 | 1.637 | 0.38976 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
4 | Kit 4 | ICB | Nos. | 15465 | 49 | 0.075778 | 0.018042 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
5 | Kit 5 | ICB | Nos. | 463956 | 35 | 1.6238 | 0.38663 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
6 | Kit 6 | ICB | Nos. | 185582 | 54 | 1.0021 | 0.23861 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
7 | Kit 7 | ICB | Nos. | 61861 | 55 | 0.34024 | 0.081008 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
| Sub-Total |  |  |  |  | 9.7635 | 2.3246
E) Diagnostic Kits (TI)
1 | RPR Kits | ICB | Tests | 4152602.8797 | 2 | 0.83052 | 0.19774 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
2 | TPHA Kits | ICB | Tests | 415260.288 | 5 | 0.20763 | 0.049436 | 2009-04-30 | 2009-05-05 | 2009-05-12 | 2009-06-30 | 2009-07-15 | 2009-07-22 | 2009-07-30 | 2009-08-14 | 2009-10-01 | 2010-03-31
| Sub-Total |  |  |  |  | 1.0382 | 0.24718
F) OST Drugs
1 | OST Drugs | ICB | Nos. | to be ascertained | -- | 7 | 1.6667 | not yet finalized | not yet finalized | not yet finalized | not yet finalized | not yet finalized | not yet finalized | not yet finalized | not yet finalized | not yet finalized | not yet finalized
| Sub-Total |  |  |  |  | 7 | 1.6667
G) IEC
1 | Printing and Supply of IEC material such Operational Guidelines and Training Manuals etc. | NS | Nos. | as per requirements | as per requirements | 1 | 0.2381 | 2009-10-01 | -- | 2009-10-15 | 2009-11-01 | -- | -- | 2009-12-01 | 2009-12-15 | 2010-02-01 | 2010-03-31
| Sub-Total |  |  |  |  | 1 | 0.2381
| Total |  |  |  |  | 137.7325 | 32.7935