## Services 2009-10
Procurement Plan for Services - NACP-III for the F.Y. 2009-10
SL No. | Description of Services | Estimated Cost (Rs. Millions) | Methods of Selection | Advertising for Short-listing (Date) | TOR/ Shortlist to be Finalized (Date) | RFP (Draft) to be forwarded to the Bank (Date) | No Objection from Bank for TOR/ Shortlist/ Final RFP (Date) | RFP Issued (Date) | Proposals to be received by NACO (Date) | Evaluation to be Finalized (Date) | No Objection by the Bank (Date) | Contract signing date | Expenditure to be incurred (Rs. Millions)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Year 2009-10 |  |  |  | 2010-11
1 | Setting up 'State Training and Resource Centre' (STRC) in Delhi to Strengthen Capacity of targeted Intervention Projects in the State of Delhi | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
2 | Setting up STRC in Rajasthan to Strengthen Capacity of targeted Intervention Projects in the State of Rajasthan | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-09-15 | 0 | 0.84 | 0.84 | 0.56 | 0.28
3 | Setting up STRC in Uttarakhand and Himanchal Pradesh to Strengthen Capacity of targeted Intervention Projects in n the State of Uttarakhand and Himanchal Pradesh | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-09-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
4 | Setting up STRC in Gujarat to Strengthen Capacity of targeted Intervention Projects in the State of Gujarat and Daman & Diu. | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
5 | Setting up STRC in Chandigarh to Strengthen Capacity of targeted Intervention Projects in the State of Punjab, Haryana and Chandigarh. | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-09-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
6 | Setting up STRC in Orissa to Strengthen Capacity of targeted Intervention Projects in the State of Orissa | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-09-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
7 | Setting up STRC in Kerala to Strengthen Capacity of targeted Intervention Projects in the State of Kerala and Lakshadweep | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-04 | 0 | 0.84 | 0.84 | 0.56 | 0.28
8 | Setting up STRC in M.P. to Strengthen Capacity of targeted Intervention Projects in the State of M.P. | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-10-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
9 | Setting up STRC in Chhattisgarh to Strengthen Capacity of targeted Intervention Projects in the State of Chhattisgarh | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-12-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
10 | Setting up STRC in Tamilnadu to Strengthen Capacity of targeted Intervention Projects in the State of Tamilnadu and Pondicherry | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-10-15 | 0 | 0.84 | 0.84 | 0.56 | 0.28
11 | Setting up STRC in West Bengal to Strengthen Capacity of targeted Intervention Projects in the State of West Bengal, Sikkim and Andaman | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-12-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
12 | Setting up STRC in Mizoram to Strengthen Capacity of targeted Intervention Projects in the State of Mizoram, Meghalaya and Arunachal Pradesh | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-10-15 | 0 | 0.84 | 0.84 | 0.56 | 0.28
13 | Setting up STRCs in Jammu & Kashmir to Strengthen Capacity of targeted Intervention Projects in the State of Jammu & Kashmir | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-12-01 | 0 | 0.84 | 0.84 | 0.56 | 0.28
14 | Setting up STRCs in Manipur to Strengthen Capacity of targeted Intervention Projects in the State of Manipur and Nagaland | 2.8 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2010-04-15 | 0 | 0.84 | 0.84 | 0.56 | 0.28
15 | Setting up STRC for the State of Karnataka | 2.8 |  | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-11-15 | 0 | 0.84 | 0.84 | 0.56 | 0.28
16 | Setting up STRCs in Bihar to Strengthen Capacity of targeted Intervention Projects in the State of Bihar | 2.5 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.75 | 0.75 | 0.5 | 0.25
17 | Setting up STRCs in Jharkhand to Strengthen Capacity of targeted Intervention Projects in the State of Jharkhand | 2.5 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.75 | 0.75 | 0.5 | 0.25
18 | Setting up STRCs in Assam to Strengthen Capacity of targeted Intervention Projects in the State of Assam | 2.5 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.75 | 0.75 | 0.5 | 0.25
19 | Setting up STRCs in U.P. to Strengthen Capacity of targeted Intervention Projects in the State of U.P. | 2.5 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.75 | 0.75 | 0.5 | 0.25
20 | Setting up STRCs in Maharashtra to Strengthen Capacity of targeted Intervention Projects in the State of Maharashtra | 2.5 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.75 | 0.75 | 0.5 | 0.25
21 | Setting up STRCs in Andhra Pradesh to Strengthen Capacity of targeted Intervention Projects in the State of Andhra Pradesh | 2.5 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-07-15 | -- | 2009-08-01 | 0 | 0.75 | 0.75 | 0.5 | 0.25
22 | STI / RTI service delivery through network of preferred private provides in 91 priority districts divided into 14 sub-Zones (14 Contracts) | 60 | SSS | -- | 2009-05-15 | -- | -- | 2009-05-22 | 2009-06-15 | 2009-06-25 | -- | 2009-07-01 | 0 | 18 | 18 | 12 | 6
23 | Campaign on HIV/AIDS on All India Radio | 50 | SSS | -- | -- | -- | -- | -- | 2009-05-15 | -- | -- | 2009-07-01 | 0 | 20 | 20 | 5 | 0
24 | Campaign on HIV/AIDS on Doordarshan | 100 | SSS | -- | -- | -- | -- | -- | 2009-04-15 | -- | -- | 2009-07-01 | 0 | 40 | 40 | 10 | 0
25 | Special Interactive Campaign on HIV/AIDS through Performing Arts such as Folk Theatre, Puppetry, street plays etc. | 20 | SSS | 2009-04-15 | 2009-05-30 | -- | 2009-06-30 | -- | -- | -- | -- | 2009-08-01 | 0 | 0 | 10 | 10 | 0
26 | Airing of episode of New Radio Programme with community mobilization for Broadcast on All India Radio | 20 | SSS | .. | .. | .. | .. | .. | 2009-05-05 | .. | .. | 2009-07-01 | 0 | 0 | 10 | 10 | 0
27 | Impact Study of various Media Campaign | 5 | SSS | -- | 2009-04-30 | -- | -- |  | 2009-06-12 | 2009-06-12 | -- | 2009-07-01 | 0 | 0 | 2.5 | 2.5 | 0
28 | Setting up of 'HIV Help Line' for Hindi speaking states | 5 | QBS | 2009-04-12 | 2009-05-31 | -- | -- | 2009-06-07 | 2209-06-28 | 2009-07-15 | -- | 2009-09-01 | 0 | 0 | 2.5 | 2.5 | 0
29 | Event Management on World AIDS Day on 1st December, 2009 | 5 | QBS | 2009-06-15 | 2009-08-13 | -- | -- | 2009-08-20 | 2009-09-21 | 2009-10-15 | -- | 2009-11-01 | 0 | 0 | 1 | 4 | 0
30 | Impact Evaluation of Targeted Interventions (TIs) | 7 | QBS | [8 empty] | 2009-05-01 | 0 | 0 | 2.8 | 4.2 | 0
31 | Consultancy for Hiring of Media Planning, Buying and Monitoring Agency for 3 years | 20 | QCBS | done | done | 2009-04-30 | 2009-05-15 | 2009-05-18 | 2009-06-16 | 2009-07-30 | 2009-07-15 | 2009-08-01 | 0 | 0 | 3.5 | 3.5 | 0
32 | Various Media Buying's through NFDC / selected media buying agency for broadcast / airing Spots on various themes including ICTC, PPTCT, ART, VBD, Stigma & Discrimination, HIV-TB, STI | 250 | SSS | -- | 2009-07-01 | -- | -- | -- | -- | -- | -- | 2009-07-15
33 | Selection of Creative Agency for 3 years | 60 | QCBS | 2008-07-03 | 2008-08-20 | 2008-10-10 | 2008-10-23 | 2008-11-11 | 2008-12-10 | 2009-03-25 | 2009-05-01 | 2009-07-15 | 2.8 | 1.4 | 1.4 | 1.4 | 0
34 | Production and Telecast of Episodes on HIV/AIDS on TV News Channels (Hindi) | 20 | QBS | 2008-05-28 | 2008-08-22 | 2008-10-23 | 2008-11-04 | 2008-11-17 | 2008-12-16 | 2009-03-25 | 2009-05-01 | 2009-07-15 | 2.8 | 1.4 | 1.4 | 1.4 | 0
35 | Production and Telecast of Episodes on HIV/AIDS on TV News Channels (English) | 20 | QBS | 2008-05-28 | 2008-08-22 | 2008-10-23 | 2008-11-04 | 2008-11-17 | 2008-12-16 | 2009-03-25 | 2009-05-01 | 2009-07-15 | 2.8 | 1.4 | 1.4 | 1.4 | 0
36 | Production of Short Films targeting Female Sex Workers (FSWs) and Injecting Drug Users (IDUs) | 1.5 | QBS | 2008-07-04 | 2008-08-23 | …… | ….. | 2009-03-17 | 2009-04-02 | 2009-04-15 | -- | 2009-07-15 | 0 | 1.5 | 0 | 0 | 0
37 | Multi-Media Campaign in Nagaland Targeting Youth | 7.5 | QBS | 2008-07-16 | 2008-09-13 | 2008-11-21 | ….. | 2009-04-06 | 2009-05-05 | 2009-05-20 | -- | 2009-07-15 | 0 | 0 | 3.75 | 3.75 | 0
38 | Multi-Media Campaign in Mizoram Targeting Youth | 7.5 | QBS | 2008-07-16 | 2008-09-13 | 2008-11-21 | ….. | 2009-04-06 | 2009-05-05 | 2009-05-20 | -- | 2009-07-15 | 0 | 0 | 3.75 | 4.75 | 0
39 | Multi-Media Campaign in Manipur Targeting Youth | 7.5 | QBS | 2008-07-16 | 2008-09-13 | 2008-11-21 | ….. | 2009-04-06 | 2009-05-05 | 2009-05-20 | -- | 2009-07-15 | 0 | 0 | 3.75 | 5.75 | 0
40 | Hiring of Agency for Media Monitoring, Buying and Monitoring for 3 years | 20 | QCBS | 2008-07-24 | 2008-08-22 | 2009-04-15 | 2009-05-01 | 2009-05-04 | 2009-06-03 | 2009-06-25 | 2009-07-05 | 2009-08-15 | 0 | 0 | 3.5 | 3.5 | 0
41 | Agency for management of Re-running of Red Ribbon Express | 40 | CQS | -- | 2009-05-01 | -- | -- | 2009-05-07 | 2009-05-22 | 2009-06-01 | -- | 2009-06-05 | 0 | 0 | 3 | 3 | 0
42 | Running of Red-Ribbon Express Train (Indian Railways) | 25 | SSS | -- | 2009-06-12 | -- | -- | 2009-06-15 | 2009-06-22 | 2009-06-25 | -- | 2009-07-01
43 | Agency for Post Audit of Procurement Under NACP-III | 7 | SSS | -- | 2009-04-30 | -- | 2009-05-07 | 2009-05-11 | 2009-05-25 | 2009-06-15 | -- | 2009-07-01
44 | Hiring of Procurement Agent (PA) for NACO for 3 years | 50 | QCBS | 2008-08-13 | 2008-11-06 | 2008-11-17 | 2008-12-22 | 2009-01-12 | 2009-04-30 | 2009-05-31 | 2009-06-15 | 2009-07-01
45 | Agency for conducting Management Audit focusing review of the oversight arrangements over Tis (Evaluation, appraisal and internal audit etc.) | 7 | QCBS | 2009-05-15 | 2009-06-30 | -- | -- | 2009-07-15 | 2009-08-13 | 2009-09-30 | -- | 2009-10-15
46 | Extension of Existing contracts for Management of Technical Support Units | 40 | SSS | -- | 2009-04-30 | -- | -- | -- | -- | 2009-05-07 | 2009-05-15 | 2009-06-01
47 | Extension of Existing contracts for Internal Audit of SACS for the year 2008-09 | 10 | SSS | -- | -- | -- | -- | -- | -- | 2009-06-01 | -- | 2009-07-01
48 | Studies prior to Mid Term Review of NACP-III | 10 | CQS/ SSS | -- | -- | -- | -- | 2009-06-01 | 2009-06-21 | 2009-07-15 | -- | 2009-08-01
| Total | 932 | [10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!